## 1.PM
General | [11 empty] | Solid Oral |  | 0
Project Name | Levetiracetam Tablets | [11 empty] | UOM
Strengths | 250 | 500 | 750 | 1000 | [8 empty] | mg | 0
| TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
SAP CODE / E Project Code
Market | US | EU | Canada | ROW | DOM
| FALSE | FALSE | FALSE | TRUE | FALSE
Business rationale |  |  |  |  | Reference Product Detail |  |  | API Details |  | API 1 | API 2 | API 3 | API 4
[5 empty] | Brand |  |  | Molecule |  | Levetiracetam Tablets
[5 empty] | Applicant |  |  | API Sourcing |  | Outsourced
Scope and Objectives |  |  |  |  | Country |  |  | API Vendor |  | VNAI |  |  |  | For Transfer Projects only
[5 empty] | Indication |  |  | Formulation Details |  |  | Form R&D Division |  | EP20-AHD | Transfer Form R&D Division
BE requirement (Required/ Not required) | [7 empty] | Product Type |  | IR | Project Initiation Date |  | 2021-07-27 | Previous Project Code
No of Approved ANDAs |  | Filing Type | [5 empty] | Packaging Type |  |  | R&D Head | Dr. Deepak Gondaliya |  | Sink Cost
Patent Status |  | Sponsor/Business Partner |  | Emcure |  |  |  | Manufacturing Plant |  | EP04-EOU(H) | Project Mngr | Ishan Rajapurkar |  | R&D Head
Commercial Details ( USA )
Strength (API 1) | 250 | 500 | 750 | 1000 | [8 empty] | Total
Strength (API 2)
Strength (API 3)
Strength (API 4)
Market Size (USD Mn) |  |  | 16.9 | [9 empty] | 16.9
Market Share Considered
Price discounting | [12 empty] | 0%
Potential Rev (USD Mn) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SU (IMS Volume) | [12 empty] | 0
Commercial Batch Size (Qtr) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 1 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 2 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 3 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 4 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 1 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 2 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 3 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 4 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial Details ( EU)
Strength (API 1) | [12 empty] | Total
Strength (API 2)
Strength (API 3)
Strength (API 4)
Market Size (USD Mn) | [12 empty] | 0
Market Share Considered
Price discounting | [12 empty] | 0%
Potential Rev (USD Mn) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SU (IMS Volume) | [12 empty] | 0
Commercial Batch Size (Qtr) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 1 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 2 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 3 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 4 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 1 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 2 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 3 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 4 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial Details (CANADA)
Strength (API 1) | [12 empty] | Total
Strength (API 2)
Strength (API 3)
Strength (API 4)
Market Size (USD Mn) | [12 empty] | 0
Market Share Considered
Price discounting | [12 empty] | 0%
Potential Rev (USD Mn) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SU (IMS Volume) | [12 empty] | 0
Commercial Batch Size (Qtr) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 1 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 2 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 3 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total API 4 Req (IMS KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 1 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 2 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 3 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 4 Req (Emcure KG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.1.FDGL-US
General | [13 empty] | TOTAL PROJECT EXPENSES | Project Source | Prev. R&D Div. | Prev. Code
Project Name |  | Levetiracetam Tablets | [12 empty] | NEW
Strengths |  | 250 mg | 500 mg | 750 mg | 1000 mg | [9 empty] | Sink Cost (Cost Endured & pre. R&D Div.
SAP Code/Project Codes | [14 empty] | 0
Imprinting/embossing codes | [13 empty] | 194.861 | TOTAL PROJECT COST | 194.861
TOTAL EXPENSES (US) |  | 44.6048 | 39.3116 | 42.8788 | 68.0657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Complexity |  | 3 | Test License Availability |  |  | LYO CYCLE | Budget and timelines submission date | 2021-07-27 | Formulation GL |  | Dr. Rushil Shah |  |  | EP20-AHD |  | Includes Cost @ all R&D division + Litigation cost (if any)
Product Type |  | IR | AHD | BHS | HNJ |  |  |  | Analytical GL |  | Munish Buch
|  |  | TRUE | FALSE | FALSE | FALSE
Batch Size |  | (Number of | Tablets | [10 empty] | 2
Strength (API 1) |  | 250 | 500 | 750 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strength (API 2) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strength (API 3) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strength (API 4) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prototype formulation |  | 50000 | 50000 | 50000 | 50000
Scale-up batch |  | 100000 | 100000 | 100000 | 100000
Exhibit Batch 1 |  | 100000 | 100000 | 100000 | 100000
Exhibit Batch 2 |  | 100000 | 100000 | 100000 | 100000
Exhibit Batch 3 |  | 110000 | 110000 | 110000 | 110000
|  | 310000 | 310000 | 310000 | 310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 1 Requirement |  | Levetiracetam Tablets | [8 empty] | Market Price (₹/kg) |  | 3600 | TOTAL
Prototype |  | 12.5 | 25 | 37.5 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125
Scale-up |  | 25 | 50 | 75 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
Exhibit Batch (I) |  | 25 | 50 | 75 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
Exhibit Batch (II) |  | 25 | 50 | 75 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
Exhibit Batch (III) |  | 27.5 | 55 | 82.5 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275
Cost | Prototype | 45000 | 90000 | 135000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000
| Scale up | 90000 | 180000 | 270000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
| Exhibit Batch | 279000 | 558000 | 837000 | 1116000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790000
TOTAL COST |  | 414000 | 828000 | 1242000 | 1656000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140000
API 2 Requirement |  | NOT APPLICABLE | [8 empty] | Market Price (₹/kg) |  |  | TOTAL
Prototype |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scale-up |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (I) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (II) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (III) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost | Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scale up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exhibit Batch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 3 Requirement |  | NOT APPLICABLE | [8 empty] | Market Price (₹/kg) |  |  | TOTAL
Prototype |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scale-up |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (I) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (II) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (III) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost | Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scale up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exhibit Batch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
API 4 Requirement |  | NOT APPLICABLE | [8 empty] | Market Price (₹/kg) |  |  | TOTAL
Prototype |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scale-up |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (I) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (II) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhibit Batch (III) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost | Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scale up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exhibit Batch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prototype | 45000 | 90000 | 135000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scale up | 90000 | 180000 | 270000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exhibit Batch | 279000 | 558000 | 837000 | 1116000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Excipient Requirement | [13 empty] | TOTAL
₹/kg | Exp. (prototype) | (Mg per unit dosage form) | [11 empty] | Cost | Quantity
1500 | Croscarmellose sodium | 10.75 | 21.5 | 32.25 | 43 | [8 empty] | 8062.5 | 5.375
1500 | Macrogol 6000 | 2.5 | 5 | 7.5 | 10 | [8 empty] | 1875 | 1.25
630 | Silica Colloidal Anhydrous (Aerosil 200 Pharma) | 5.19 | 10.375 | 15.57 | 20.76 | [8 empty] | 1634.6925 | 2.5947
480 | Magnesium Stearate (Ligamed MF-2-V) | 0.32 | 0.625 | 0.95 | 1.26 | [8 empty] | 75.72 | 0.15775
3500 | Opadry | 8.07 | 16.125 | 24.2 | 32.26 | [8 empty] | 14114.625 | 4.0328
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0 | COST |  | QUANTITY
₹/kg | Exp. (Scale up & EB) | (Mg per unit dosage form) | [11 empty] | Cost | Quantity | Scale Up | Exhibit Batch | Scale Up | Exhibit Batch
1500 | Croscarmellose sodium | 10.75 | 21.5 | 32.25 | 43 | [8 empty] | 66112.5 | 44.075 | 16125 | 49987.5 | 10.75 | 33.325
1500 | Macrogol 6000 | 2.5 | 5 | 7.5 | 10 | [8 empty] | 15375 | 10.25 | 3750 | 11625 | 2.5 | 7.75
630 | Silica Colloidal Anhydrous (Aerosil 200 Pharma) | 5.19 | 10.375 | 15.57 | 20.76 | [8 empty] | 13404.4785 | 21.2769 | 3269.385 | 10135.0935 | 5.1895 | 16.0875
480 | Magnesium Stearate (Ligamed MF-2-V) | 0.32 | 0.625 | 0.95 | 1.26 | [8 empty] | 620.904 | 1.2935 | 151.44 | 469.464 | 0.3155 | 0.97805
3500 | Opadry | 8.07 | 16.125 | 24.2 | 32.26 | [8 empty] | 115739.925 | 33.0686 | 28229.25 | 87510.675 | 8.0655 | 25.0031
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
[14 empty] | 0 | 0 |  |  | 0 | 0
Cost | Prototype | 2577.165 | 5151.1875 | 7729.505 | 10304.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25762.5375
| Scale up | 5154.33 | 10302.375 | 15459.01 | 20609.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51525.075
| Exhibit Batch | 15978.423 | 31937.3625 | 47922.931 | 63889.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159727.7325
Total Cost |  | 23709.918 | 47390.925 | 71111.446 | 94803.056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237015.345
Hard Gelatin Capsule Shells |  |  | NOT APPLICABLE | [10 empty] | TOTAL
Size of Capsule Shell |  | Size 4 | Size 2 | [11 empty] | #N/A
#N/A
Cost | Prototype |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scale up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exhibit Batch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Packaging Material Requirement | [13 empty] | TOTAL
₹/Ut. | Prototype Formulation Development
480 | Aluminium Foil (25µ) | 3 | 3 | 3 | 3 | [8 empty] | 12 | 2
255 | PVC/PVDC Foil (250/90) | 3 | 3 | 3 | 3 | [8 empty] | 12 | 2
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
₹/Ut. | Scale Up | [13 empty] | #N/A
480 | Aluminium Foil (25µ) | 5 | 5 | 5 | 5 | [8 empty] | 20 | 2
255 | PVC/PVDC Foil (250/90) | 5 | 5 | 5 | 5 | [8 empty] | 20 | 2
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
₹/Ut. | Exhibit Batch | [13 empty] | #N/A
480 | Aluminium Foil (25µ) | 150 | 150 | 150 | 150 | [8 empty] | 600 | 2
255 | PVC/PVDC Foil (250/90) | 150 | 150 | 150 | 150 | [8 empty] | 600 | 2
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
[14 empty] | 0 | #N/A
Cost | Prototype | 2205 | 2205 | 2205 | 2205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8820
| Scale up | 3675 | 3675 | 3675 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14700
| Exhibit Batch | 110250 | 110250 | 110250 | 110250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441000
TOTAL COST |  | 116130 | 116130 | 116130 | 116130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464520
Analytical Activities | [13 empty] | TOTAL
₹/Test. | Prototype Development
1250 | T001: Assay by HPLC | 30 | 30 | 30 | 30 | [8 empty] | 150000
4000 | T008: Dissolution Profile by HPLC | 5 | 5 | 5 | 5 | [8 empty] | 80000
2000 | T009: Dissolution single point by HPLC | 30 | 30 | 30 | 30 | [8 empty] | 240000
8000 | T011: Dissolution Profile by HPLC 12 units | 5 | 5 | 5 | 5 | [8 empty] | 160000
20000 | T022: Method Development for Assay | 1 | [11 empty] | 20000
22000 | T023: Method Development for dissolution | 1 | [11 empty] | 22000
25000 | T024: Method Development for RS | 1 | [11 empty] | 25000
2500 | T027: Related Substances by HPLC | 30 | 30 | 30 | 30 | [8 empty] | 300000
200 | T030: Uniformity of Dosage units by weight variation | 10 | 10 | 10 | 10 | [8 empty] | 8000
300 | T034: Water Content (by KF) | 30 | 30 | 30 | 30 | [8 empty] | 36000
2500 | T037: Blend uniformity | 3 | 3 | 3 | 3 | [8 empty] | 30000
2500 | T040: Residual solvents | 3 | 3 | 3 | 3 | [8 empty] | 30000
300 | T043: Identification by HPLC | 5 | 5 | 5 | 5 | [8 empty] | 6000
3000 | T048: Particle size | 3 | 3 | 3 | 3 | [8 empty] | 36000
1200 | T051: X-ray Diffraction (XRD) | 15 | 15 | 15 | 15 | [8 empty] | 72000
4000 | T038: Microbial Limit Test | 3 | 3 | 3 | 3 | [8 empty] | 48000
₹/Test. | Scale Up
1250 | T001: Assay by HPLC | 15 | 15 | 15 | 15 | [8 empty] | 75000
4000 | T008: Dissolution Profile by HPLC | 5 | 5 | 5 | 5 | [8 empty] | 80000
2000 | T009: Dissolution single point by HPLC | 15 | 15 | 15 | 15 | [8 empty] | 120000
8000 | T011: Dissolution Profile by HPLC 12 units | 5 | 5 | 5 | 5 | [8 empty] | 160000
2500 | T027: Related Substances by HPLC | 15 | 15 | 15 | 15 | [8 empty] | 150000
200 | T030: Uniformity of Dosage units by weight variation | 10 | 10 | 10 | 10 | [8 empty] | 8000
300 | T034: Water Content (by KF) | 15 | 15 | 15 | 15 | [8 empty] | 18000
2500 | T037: Blend uniformity | 1 | 1 | 1 | 1 | [8 empty] | 10000
2500 | T040: Residual solvents | 1 | 1 | 1 | 1 | [8 empty] | 10000
3000 | T048: Particle size | 1 | 1 | 1 | 1 | [8 empty] | 12000
1200 | T051: X-ray Diffraction (XRD) | 5 | 5 | 5 | 5 | [8 empty] | 24000
4000 | T038: Microbial Limit Test | 3 | 3 | 3 | 3 | [8 empty] | 48000
₹/Test. | Exhibit Batch
1250 | T001: Assay by HPLC | 45 | 45 | 45 | 45 | [8 empty] | 225000
4000 | T008: Dissolution Profile by HPLC | 15 | 15 | 15 | 15 | [8 empty] | 240000
2000 | T009: Dissolution single point by HPLC | 45 | 45 | 45 | 45 | [8 empty] | 360000
8000 | T011: Dissolution Profile by HPLC 12 units | 15 | 15 | 15 | 15 | [8 empty] | 480000
2500 | T027: Related Substances by HPLC | 45 | 45 | 45 | 45 | [8 empty] | 450000
3500 | T032: Uniformity of dosage unit by content uniformity (Subdivision) | 15 | 15 | 15 | 15 | [8 empty] | 210000
300 | T034: Water Content (by KF) | 45 | 45 | 45 | 45 | [8 empty] | 54000
2500 | T037: Blend uniformity | 3 | 3 | 3 | 3 | [8 empty] | 30000
2500 | T040: Residual solvents | 3 | 3 | 3 | 3 | [8 empty] | 30000
3000 | T048: Particle size | 1 | 1 | 1 | 1 | [8 empty] | 12000
1200 | T051: X-ray Diffraction (XRD) | 15 | 15 | 15 | 15 | [8 empty] | 72000
4000 | T038: Microbial Limit Test | 15 | 15 | 15 | 15 | [8 empty] | 240000
₹/Test. | AMV Cost
700000 | Method Validation | 700000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
|  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1
Cost | Prototype | 366000 | 299000 | 299000 | 299000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263000
| Scale up | 178750 | 178750 | 178750 | 178750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715000
| Exhibit Batch | 600750 | 600750 | 600750 | 600750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2403000
TOTAL COST |  | 1145500 | 1078500 | 1078500 | 1078500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4381000
Reference Product Requirement | [13 empty] | TOTAL
Unit cost of Ref. Product
Formulation Development | [13 empty] | 0
Pilot BE | [13 empty] | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pharmaceutical Equivalence | [13 empty] | 0
Pivotal Bio |  | 300000 | [11 empty] | 0
|  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 300000
| Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bio Study Cost | [13 empty] | TOTAL
Pilot Bio
A | Fasting |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
B | Fed |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
C | Number of Volunteers | 30 | 35 | 48 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143
30
D | Clinical Cost/Vol. | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
30000 | [13 empty] | 0
E | Bio analytical Cost/Vol. | 28000 | 80000 | 50000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 11000
28000 | [13 empty] | 0
F | Doc. Cost/study | 110000 | 110000 | 110000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000
110 | [13 empty] | 0
G | TOTAL COST (PILOT) | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
Pivotal Bio | [13 empty] | 0
A | Fasting |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
B | Fed |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | [13 empty] | 0
C | Number of Volunteers | 48 | 28 | 72 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48
D | Clinical Cost/Vol. | 24400 | 45000 | 50000 | 24400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24400
E | Bio analytical Cost/Vol. | 44044 | 68000 | 50000 | 44044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44044
F | Doc. Cost/study | 1000000 | 1500000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000
G | TOTAL COST (PIVOTAL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Bio Study Cost |  | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
| Pilot Bio Study | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tooling and Change part cost | [13 empty] | TOTAL
Prototype Development |  | (Unit quantities per strength…) | [11 empty] | 0
[14 empty] | 0 | GIFT SAMPLE
0
0
0
0
Cost | Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scale Up / Exhibit Batch
3000 | Tooling | 47 | 47 | 47 | 47 | [8 empty] | 564000
0
0
0
0
0
0
Cost | Scale Up / Exhibit | 141000 | 141000 | 141000 | 141000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564000
Total Cost |  | 141000 | 141000 | 141000 | 141000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564000
Capex & Miscellaneous Expenses (Prototype Formulation-Development Phase) | [13 empty] | TOTAL
Miscellaneous |  | 200000 | [11 empty] | 0
Licensing | [13 empty] | 0
Capex 1 (Packing change part) | [13 empty] | 0
Capex 2 | [13 empty] | 0
0
0
0
0
Total Cost |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Plant Support Cost | [10 empty] | Plant Utilization rate (₹/Day) |  | 168000 | TOTAL |  | EP04-EOU(H)
Scale up |  | 1 | 1 | 1 | 1 | [8 empty] | 4
Exhibit Batch |  | 3 | 3 | 3 | 3 | [8 empty] | 12
Total Cost |  | 672000 | 672000 | 672000 | 672000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2688000
0
[13 empty] | 80 | 0.3
Man Power Cost & Project Duration | [10 empty] | Man Hour rate (₹/hr) |  | 1350 | TOTAL | Duration | Project activities |  | Man power | 4 | 0 | 4 | non rld | rld
Project Initiation |  | 1.2 | 1.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8 | 2 | Project Initiation |  | 0.3 | 0.6
Literature Review & Sourcing |  | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2 | Literature Review & Sourcing |  | 2 | 4
Formulation development |  | 72 | 72 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 90 | Formulation development |  | 0.5 | 45 | 9 | 36 | 72 | 288
Analytical Development |  | 115.2 | 115.2 | 115.2 | 115.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460.8 | 60 | Analytical Development |  | 1.2 | 72 | 14.4 | 57.6 | 115.2 | 460.8
Pilot Bio Study |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Pilot Bio Study |  | 0.2 | 0
Scale Up |  | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 4 | Scale Up |  | 1 | 4
AMV & TT |  | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 15 | AMV & TT |  | 2 | 30
Exhibit Batch |  | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 12 | Exhibit Batch |  | 1 | 12
Pivotal Bio Study |  | 48 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 30 | Pivotal Bio Study |  | 0.2 | 6
Stability |  | 432 | 432 | 432 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1728 | 180 | Stability |  | 1.2 | 216
Filing |  | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 5 | Filing |  | 1 | 5 | 1 | 4 | 8 | 32
Cost | Prototype | 265140 | 265140 | 265140 | 265140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060560 | 308 | 0.84384
| Scale up | 10800 | 10800 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43200 | TOTAL MANHOURS |  | 3105.6
| Exhibit Batch | 772200 | 772200 | 772200 | 772200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3088800
Total Cost |  | 1048140 | 1048140 | 1048140 | 1048140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4192560
Filing Expenses | [13 empty] | TOTAL
23 | Canada | [12 empty] | 0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
51 | US (ANDA) Filing | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Wise Budget | [13 empty] | TOTAL | CUM. TOTAL | % of TOTAL
Feasibility |  | 12420 | 12420 | 12420 | 12420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49680 | 49680 | 0.255%
Prototype Development |  | 868502.165 | 649076.1875 | 696654.505 | 2744229.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4958462.5375 | 5008142.5375 | 25.7%
R&D Scale Up |  | 597379.33 | 692527.375 | 787684.01 | 882834.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2960425.075 | 7968567.6125 | 40.89%
AMV/AMT |  | 781000 | 81000 |  | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 943000 | 8911567.6125 | 45.73%
Exhibit & Stability |  | 2190378.423 | 2485337.3625 | 2780322.931 | 3075289.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10531327.7325 | 19442895.345 | 99.78%
Filing |  | 10800 | 10800 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43200 | 19486095.345 | 100%
Total Cost |  | 4460479.918 | 3931160.925 | 4287881.446 | 6806573.056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19486095.345

## 2.2.FDGL-EU
ADDITONAL COST INCURED FOR EU DEVELOPMENT AND FILING
Project Name
Strengths |  | 90 | 180 | 360 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A
|  | FALSE |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Reference Product Requirement | [13 empty] | TOTAL
Unit cost of Ref. Product
Formulation Development | [13 empty] | 0
Pilot BE | [13 empty] | 0
Pharmaceutical equivalence | [13 empty] | 0
Pivotal Bio | [13 empty] | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bio Study Cost | [13 empty] | TOTAL
Pilot Bio
A | Fasting | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
C | Number of Volunteers |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
18
D | Clinical Cost/Vol. |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 11000
30000 | [13 empty] | 0
F | Doc. Cost/study |  |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
200 | [13 empty] | 0
G | TOTAL COST (PILOT) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pivotal Bio | [13 empty] | 0
A | Fasting | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
C | Number of Volunteers |  |  | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
33 | [13 empty] | 0
D | Clinical Cost/Vol. |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
6000 | [13 empty] | 0
F | Doc. Cost/study |  |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
200
G | TOTAL COST (PIVOTAL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Bio Study Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capex & Miscellaneous Expenses (Prototype Formulation-Development Phase) | [13 empty] | TOTAL
Miscellaneous | [13 empty] | 0
Licensing | [13 empty] | 0
Capex 1 | [13 empty] | 0
Capex 2 | [13 empty] | 0
0
0
0
0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filing Expenses | [13 empty] | TOTAL
45 | EU Filing | [12 empty] | 0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
51 | US (ANDA) Filing | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.3.FDGL-Canada
ADDITONAL COST INCURED FOR CANADA DEVELOPMENT AND FILING
Project Name |  | Levetiracetam Tablets
Strengths | [14 empty] | #N/A
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Reference Product Requirement | [13 empty] | TOTAL
Unit cost of Ref. Product
Formulation Development | [13 empty] | 0
Pilot BE | [13 empty] | 0
Pharmaceutical equivalence | [13 empty] | 0
Pivotal Bio | [13 empty] | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bio Study Cost | [13 empty] | TOTAL
Pilot Bio
A | Fasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
C | Number of Volunteers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18
D | Clinical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
30000 | [13 empty] | 0
F | Doc. Cost/study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | [13 empty] | 0
G | TOTAL COST (PILOT) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pivotal Bio | [13 empty] | 0
A | Fasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
C | Number of Volunteers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | [13 empty] | 0
D | Clinical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | [13 empty] | 0
F | Doc. Cost/study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200
G | TOTAL COST (PIVOTAL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Bio Study Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capex & Miscellaneous Expenses (Prototype Formulation-Development Phase) | [13 empty] | TOTAL
Miscellaneous | [13 empty] | 0
Licensing | [13 empty] | 0
Capex 1 | [13 empty] | 0
Capex 2 | [13 empty] | 0
0
0
0
0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filing Expenses | [13 empty] | TOTAL
23 | Canada | [12 empty] | 0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
51 | US (ANDA) Filing | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.4.FDGL-ROW
ADDITONAL COST INCURED FOR ROW DEVELOPMENT AND FILING
Project Name |  | Levetiracetam Tablets
Strengths | [14 empty] | #N/A
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Reference Product Requirement | [13 empty] | TOTAL
Unit cost of Ref. Product
Formulation Development | [13 empty] | 0
Pilot BE | [13 empty] | 0
Pharmaceutical equivalence | [13 empty] | 0
Pivotal Bio | [13 empty] | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bio Study Cost | [13 empty] | TOTAL
Pilot Bio
A | Fasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
C | Number of Volunteers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18
D | Clinical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
30000 | [13 empty] | 0
F | Doc. Cost/study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | [13 empty] | 0
G | TOTAL COST (PILOT) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pivotal Bio | [13 empty] | 0
A | Fasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
C | Number of Volunteers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | [13 empty] | 0
D | Clinical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | [13 empty] | 0
F | Doc. Cost/study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200
G | TOTAL COST (PIVOTAL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Bio Study Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capex & Miscellaneous Expenses (Prototype Formulation-Development Phase) | [13 empty] | TOTAL
Miscellaneous | [13 empty] | 0
Licensing | [13 empty] | 0
Capex 1 | [13 empty] | 0
Capex 2 | [13 empty] | 0
0
0
0
0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filing Expenses | [13 empty] | TOTAL
45 | EU Filing | [12 empty] | 0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
51 | US (ANDA) Filing | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.5.FDGL-Domestic
ADDITONAL COST INCURED FOR DOMESTIC DEVELOPMENT AND FILING
Project Name |  | Levetiracetam Tablets
Strength | [14 empty] | #N/A
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Reference Product Requirement | [13 empty] | TOTAL
Unit cost of Ref. Product
Formulation Development | [13 empty] | 0
Pilot BE | [13 empty] | 0
Pharmaceutical equivalence | [13 empty] | 0
Pivotal Bio | [13 empty] | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prototype | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bio Study Cost | [13 empty] | TOTAL
Pilot Bio
A | Fasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
C | Number of Volunteers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18
D | Clinical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
30000 | [13 empty] | 0
F | Doc. Cost/study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | [13 empty] | 0
G | TOTAL COST (PILOT) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pivotal Bio | [13 empty] | 0
A | Fasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
B | Fed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [13 empty] | 0
C | Number of Volunteers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | [13 empty] | 0
D | Clinical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10000 | [13 empty] | 0
E | Bio analytical Cost/Vol. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | [13 empty] | 0
F | Doc. Cost/study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200
G | TOTAL COST (PIVOTAL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Bio Study Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pilot Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pivotal Bio Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capex & Miscellaneous Expenses (Prototype Formulation-Development Phase) | [13 empty] | TOTAL
Miscellaneous | [13 empty] | 0
Licensing | [13 empty] | 0
Capex 1 | [13 empty] | 0
Capex 2 | [13 empty] | 0
0
0
0
0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filing Expenses | [13 empty] | TOTAL
45 | EU Filing | [12 empty] | 0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
51 | US (ANDA) Filing | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
0
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Total Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 3.IPD
General | [9 empty] | U S A
Project Name |  | Levetiracetam Tablets
Markets |  | US |  |  |  |  | IPD Comments>> | PIII TO PDT PIV -EDP TO '209 TBD/Monitor wrt '493 & '255 applications
No. of Approved ANDAs |  | Nil | Patent Status | Patented | Legal Status (Litigation) |  | Litigation ongoing
No. of Pending ANDA App.n |  | Actavis, Teva | Type of Filing | PIV | Cost of Litigation
Patent Details
Patent Numbers |  | Original Expiry Date | Type | Extension Application | Extn. Expiry Date | Comment (Patent Specific) |  |  | Strategy
1 | US 6465504 | 2019-04-05 | Pdt |  |  | (Expiry incl of PTE) Entry after expiry |  |  | PIII
2 | US 6596750 | 2017-06-24 | MOU |  |  | Entry after expiry |  |  | PIII
3 | US9283209 | 2034-11-21 | Marketed composition-Jadenu |  |  | EDP |  |  | PIV
Innovator NON-OB
4 | US 20160220493 | 2034-11-21 | Tablet composition with disintegration time 3-10m |  |  | TBD/Monitor
5 | US 20160175255 | 2023-10-14 | Exjade Marketed comp. |  |  | TBD/Monitor
Exclusivity
Type |  | Expiry | Strategy
1 | ODE-Treatment of chronic iron overload in alpha-thalassemia | 2020-01-23
2 | PED-Possible
General | [9 empty] | E U R O P E
Project Name |  | Levetiracetam Tablets
Market |  | EUROPE |  |  |  |  | IPD Comments>> | Entry:Not before Aug.2021 TBD /Monitor - EP2964202 & EP3124018
No. of Approved ANDAs |  | Nil | Patent Status | Patented | Legal Status (Litigation)
No. of Pending ANDA App.n |  | Nil | Type of Filing | Abridged | Cost of Litigation
Patent Details
Patent Numbers |  | Original Expiry Date | Type | Extension Application | Extn. Expiry Date | Comment (Patent Specific) |  |  | Strategy
1 | EP0914118 B | 2017-06-24 | Pdt |  |  | Expiry with SPC till Aug. 30, 2021 (UK) Aug.31,2021 (DE) Aug.27, 2021 (IT) Aug.28, 2021 (FR & ES) |  |  | Entry after expiry
2 | EP2964202 A- Under examination; | 2034-03-06 | Mktd Compn(Jadenu) -Film -coated Tab.90 mg, 180 mg or 360 mg |  |  | compn without SLS & Lactose |  |  | TBD/Monitor
3 | EP3124018 (A1)-Published Feb.1, 2017
4 | EP 1556013 B-Patent maintained during oppn | 2023-10-14 | Mktd compn (Exjade) |  |  | Compn dispersible Tab. |  |  | EDP
Exclusivity
Type |  | Expiry | Strategy
1 | DE-Expired | 2016-08-31
General | [9 empty] | C A N A D A
Project Name |  | Levetiracetam Tablets
Market |  | CANADA |  |  |  | IPD Comments>>
No. of Approved ANDAs |  |  | Patent Status |  | Legal Status (Litigation)
No. of Pending ANDA App.n |  |  | Type of Filing |  | Cost of Litigation
Patent Details
Patent Numbers |  | Original Expiry Date | Type | Extension Application | Extn. Expiry Date | Comment (Patent Specific) |  |  | Strategy
Exclusivity
Type |  | Expiry | Strategy
General | [9 empty] | R O W
Project Name |  | Levetiracetam Tablets
Market |  | ROW |  |  |  | IPD Comments>>
No. of Approved ANDAs |  | 0 | Patent Status |  | Legal Status (Litigation)
No. of Pending ANDA App.n |  |  | Type of Filing |  | Cost of Litigation
Patent Details
Patent Numbers |  | Original Expiry Date | Type | Extension Application | Extn. Expiry Date | Comment (Patent Specific) |  |  | Strategy
Exclusivity
Type |  | Expiry | Strategy
General | [9 empty] | D O M E S T I C
Project Name |  | Levetiracetam Tablets
Market |  | DOM |  |  |  | IPD Comments>>
No. of Approved ANDAs |  |  | Patent Status |  | Legal Status (Litigation)
No. of Pending ANDA App.n |  |  | Type of Filing |  | Cost of Litigation
Patent Details
Patent Numbers |  | Original Expiry Date | Type | Extension Application | Extn. Expiry Date | Comment (Patent Specific) |  |  | Strategy
Exclusivity
Type |  | Expiry | Strategy

## PIF
Project Initiation Form / Code Creation
Project name |  | Levetiracetam Tablets | [9 empty] | Project start date
Strength |  | 250 mg | 500 mg | 750 mg |  |  | 1000 mg |  |  |  |  | 2021-07-27
Administrative section | [8 empty] | Commercial section
1 | Sponsor/Business Partner |  | Emcure | [5 empty] | 1 | Market |  |  |  | US | EU | Canada | ROW | DOM
3 | Product Type |  | IR |  |  | #REF! |  |  | 2 | IMS (USD Mn) |  |  |  | 16.9 | 0 | 0
4 | R&D Division |  | EP20-AHD |  |  | #REF! |  |  | 3 | Competitors |  |  |  | 0
5 | Group Leader |  | Dr. Rushil Shah |  |  | #REF! |  |  | 4 | Potential Revenue (USD Mn) |  |  |  | 1.69
6 | Complexity |  | 3 |  |  | #REF! |  |  | 5 | Patent Status |  |  |  | 0
7 | Supporting Plant |  | EP04-EOU(H) |  |  | #REF! |  |  | 6 | Filing Type |  |  |  | 0
8 | RLD | Country | US | EU | Canada |  | ROW | DOM
|  | Brand | 0 | 0
|  | Applicant | 0
9 | BE requirement |  | 0
Project Section
1 | Business Rationale |  |  |  | : | 0
2 | Scope and Objectives |  |  |  | : | 0
3 | Target date for completing milestone planning and filling up project summary template* |  |  |  | : | 2021-07-27
4 | Exploratory Budget |  |  |  | : | NA
This form needs to be filled within two days of project allocation to R&D
Note
[*]- Final allocation of budget will be made on approval of Project Charter Summary
[*]- In Filing type; For non-US PIFs: Type – I = No IP Comments; Type – II = IP TBD
|  | Dr. Rushil Shah |  |  | Dr. Jayant Tilekar |  |  |  |  | Mr. Ramesh Pimple | #N/A | #N/A | #N/A | US (ANDA) Filing | Dr. Dinesh Kumar B
|  | Group Leader, F&D |  |  | Project Management |  |  |  |  | Regulatory Affairs |  |  |  |  | Intellectual Property

## Project Charter.
Project Budget Form
Project name | Levetiracetam Tablets
Strengths | 250 mg | 500 mg | 750 mg | 1000 mg
Projects Code
Head-Wise Budget (INR Lacs) | [5 empty] | Project Details
Budget Heads |  | Prototype | Scale Up | Exhibit | TOTAL | Market | US | EU | Canada | ROW | DOM
Total Manpower Cost |  | 10.6056 | 0.432 | 30.888 | 41.9256 | Sponsor/Business Partner | Emcure
Total Raw material Cost |  | 4.8458 | 9.6623 | 33.9073 | 48.4154 | Group Leader | Dr. Rushil Shah
Plant Support Cost |  | 0 | 6.72 | 20.16 | 26.88 | Project Complexity | 3 | (on 1-5 Scale)
Reference Product Cost |  | 0 | 0 | 3 | 3 | Total Project Duration | 308
Analytical Cost |  | 12.63 | 7.15 | 31.03 | 50.81 | API | Levetiracetam Tablets |  | 0 | 0
Bio Study Cost * |  | 20 | 0 | 0 | 20 | API Source | Outsourced | 0 | 0 | 0
Toolings & Change Parts |  | 0 | 5.64 | 0 | 5.64 | API Commercial Quantity | 0 | 0 | 0 | 0
Other Expenses |  | 2 | 0 | 0 | 2 | API price in (₹/kg) | 3600
Filing Expenses |  | 0 | 0 | 0 | 0 | API Requirement (kg) | Levetiracetam Tablets |  | 0 | 0
TOTAL |  | 50.0814 | 29.6043 | 118.9853 | 198.671 | Prototype | 125 | 0 | 0 | 0
[6 empty] | Scale-up | 250 | 0 | 0 | 0
[6 empty] | Exhibit | 775 | 0 | 0 | 0
Cumulative Phase-Wise Budget (INR Lacs) | [5 empty] | Deliverabales
Cost Heads |  | % of Total |  | Cost (Rs. Lacs) |  | Pharmacoepial Standards on Quality | US | EU | Canada | ROW | DOM
Feasibility |  | 0.255% |  | 0.4968
Prototype Devt |  | 25.7% |  | 50.0814 |  | Project Budget (INR Lacs) | 194.861 | 0 | 0 | 0
R&D Scale-up |  | 40.89% |  | 79.6857 |  | Project Completion/Filing Date | 2022-05-31
AMV/AMT |  | 45.73% |  | 89.1157
Exhibit/Stability |  | 99.78% |  | 194.429 |  | BE Studies | FTR
Filing |  | 100% |  | 194.861
ADDITIONAL COST TO INCUR FOR EU MARKET (INR Lacs)
[6 empty] | Reference Product Cost | 0
[6 empty] | Bio Study Cost | 0
ADDITIONAL COST TO INCUR FOR ROW AND DOMESTIC MARKET (INR Lacs) | [5 empty] | Capex and Misc. Cost | 0
Reference Product Cost |  | 0 |  |  |  | Filing Cost | 0
Bio Study Cost |  | 0 |  |  |  | TOTAL | 0
Capex and Misc. Cost |  | 0
Filing Cost |  | 0 |  |  |  | ADDITIONAL COST TO INCUR FOR CANADA MARKET (INR Lacs)
TOTAL |  | 0 |  |  |  | Reference Product Cost | 0
[6 empty] | Bio Study Cost | 0
[6 empty] | Capex and Misc. Cost | 0
[6 empty] | Filing Cost | 0
TOTAL BUDGET |  |  | 194.861 |  |  | TOTAL | 0
Please Note:
Pilot Bio Cost Considered in Budget.
Bio Cost not considered in R&D budget, and same is considered in 'Business Unit Cost Center' of Emerging Market.
Dr. Rushil Shah |  |  |  |  | Dr. Deepak Gondaliya |  | Mr. Rohit Pant
Associate Director (R&D) |  |  |  |  | President, Manufacturing |  | President, Emerging Market
Mr. Sanjay Mehta |  |  |  | Mr. Mahesh Lolage |  | Mr. Samit Mehta
President Commercial |  |  |  | Project Management |  | President - Operations

## Activity Duration (hidden)
Task Name |  |  | Duration
Project selection |  |  | 0
RLD Selection
Project given to R&D for development
Decision on API source (In-house or Outsourced)
Project initiation |  |  | 0
Project allocation
Initiation Literature Review
API Calculation
Acquire Test Licence
Project code creation
Project planning |  |  | 0
Detailed activity wise project plan
CFT meeting & activity detailing
Product Literature review |  |  | 0
RLD Literature study
Idenitification of required materials
Probable Manufacturing process
Non infringement check & Patent study
Sourcing/ Purchase |  |  | 0
| Procurement of RLD |  | 0
Calculation of RLD requirement
Import license application
Purchase of RLD
| Sourcing of API |  | 0
Vendor identification and shortlisting
API requirement communication (Quantity and Specification)
Acquiring specs and quotations from vendors
Specification / CoA review
Query Resolution from vendor
NI Analysis
Finalization and CDA Signing
Purchase requisition (PR)
Acquiring of proforma invoice
Import license
PO and purchase of API
Development timelines from API team (In-House API)
API receipt date for development
| Sourcing of RM and excipients |  | 0
Material Grade Selection
Purchase requisition (PR)
PO and purchase of Material
Material receipt date for development
| Sourcing of specific analytical requirements |  | 0
Identification of any special requirement for DP
Identification and finalization of vendors
Purchase requisition
PO and Purchase of Requirement
Formulation development |  |  | 0
| Prototype development |  | 0
Preformulation study
Initial development trials
Refining of formulation to match target profile
Prototype Formulation stability
Formulation & Process optimization studies
Finalization of formulation at R&D scale
IPD & RA clearance on finalized formulation
| Documentation Activities |  | 0
Initiation and draft PDR
NPP Initiation
ADE report
CMV requirement evaluation
TDP Finalization
Analytical development |  |  | 0
| RM and API method development |  | 0
Discussion on usage of vendor methods along with CDA
Receipt from Vendor (API, MOA, Specs & AMV)
Vendor method feasibility study
Finalizing Method for analysis
| Method development for Drug product |  | 0
Assay, BU and CU method development
Solubility study
Disso method development
RS method development
Analysis of preformulation samples
Additional test development
Cleaning method development
| Routine analytical support |  | 0
Disso tests
Assay, BU and CU tests
RS tests
Multimedia disso tests
Additional analysis
R&D stability |  |  | 0
Stability of R&D batches
Analysis of 3 M stability batch
Analysis of 6 M stability batch
Pilot bio studies |  |  | 0
| Documentation Activities |  | 0
Literature search
Acquiring BE NOC
Preparation of protocol synopsis
Identification of CRO
Finalization of protocols with CRO
Request for slots with CRO
IPD & RA Clearance
| Study |  | 0
Receipt of study samples
Study duration
Review of data received
Post pilot bio reformulation |  |  | 0
CFT to decide course of development
Formulation alteration and/or freezing
Specifications/STP preparation |  |  | 0
RM specs preparation
RM specs approval
Draft FP specs preparation
Scaleup |  |  | 0
| Preparation for scaleup activity |  | 0
Code creation meeting
Preparation of BOM for RM and PM
Approval of BOM
Scaleup BMR & protocols preparation
Protocol approval
CMV activity
Procurement of API for scaleup - PR and purchase
Procurement of RM for scaleup - PR and purchase
Check for slot availability
IPD & RA Clearance
| Scaleup activity |  | 0
Material release & transfer
Scale up batch manufacturing
Hold time study
Analysis of scaleup samples
Scale-up report
Finalization of formulation & process
Finalization of specifications/STP |  |  | 0
Specification revision and/or freezing
Approval of freezed specification
Analytical method validation |  |  | 0
| API & RM AMV |  | 0
Protocol preparation
Protocol approval
Validation activity
Validation report preparation
Report approval
| Drug product AMV |  | 0
Protocol preparation
Protocol approval
Validation activity
Validation report preparation
Report approval
Post validation changes and finalization of specs
Technology Transfer |  |  | 0
| Formualtion details transfer |  | 0
Tech pack preparation
Tech pack approval
Tech Transfer meeting
| Drug product analytical method transfer |  | 0
AMT protocol
Protocol approval
AMT activity
Method transfer report
| API and RM method transfer |  | 0
AMT protocol
Protocol approval
API AMT activity
Method transfer report
CQA Specs
Exhibit batch |  |  | 0
| Preparation for Exhibit |  | 0
Vendor qualification
Approved vendor list
MRN for API, raw materials and packaging materials
Procurement of materials if not available inhouse or in store
RM/ PM release
Slot finalization
| Exhibit batch execution |  | 0
Preparation & approval of MFR, BMR, BPR, PEP etc.
Exhibit batch preparation (3 batches for 1 strength)
Exhibit batch analysis
Packaging
Stability |  |  | 0
Stability Charging
Stability 1 M analysis & review
Stability 3 M analysis & review
Stability 6 M analysis & review
Pivotal bio |  |  | 0
| Scope of study finalization |  | 0
RLD purchase
Literature search (if pilot not done)
Preparation of protocol synopsis by BE team
Application for NoC (if required) to DCGI
Identification of CRO
Submission of synopsis to CRO
Review and finalization of protocols received
Request for slots in CRO
| Pivotal bio activity |  | 0
Receipt of samples from plant QA for study
Carrying out of the study by CRO
Receipt of bio data, review and application
ANDA Filing |  |  | 0
NI Analysis & Label Review
Dossier compilation from R&D and plant
CQ Review
ANDA submission

## Graphs
General
Project Name |  | Levetiracetam Tablets
Strengths |  | 250 mg | 500 mg | 750 mg | 1000 mg
SAP Code/Project Codes
| Potential Revenue ($) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Potential Revenue (INR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Development Exp | 44.6048 | 39.3116 | 42.8788 | 68.0657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | $ 1 (USD) | 67
Potential Annual Revenue Vs Development Expenses | [13 empty] | 0 | -194.861
0 | [13 empty] | 194.861
194.861
COMMERCIAL REQUIREMENT PER QUARTER | [13 empty] | 0 | 0
0
| Commercial Volume per QTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| API 1 Cost (INR/kg) | #REF!
| API 2 Cost (INR/kg) | 0
| Strength 1 | 250 | 500 | 750 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Strength 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| API 1 Used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| API 2 Used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total cost of APIs | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Excp & pkg Cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Plant running cost /day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| No. of Days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Man Power | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Man power cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL PROJECTED COST | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Projected Commercial batch Cost | [13 empty] | 0 | 0
0
Active Pharmaceuticals Ingredient Cost
41.4
RM & Packaging Cost | Prototype | 4782.165 | 7356.1875 | 9934.505 | 12509.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scale Up | 8829.33 | 13977.375 | 19134.01 | 24284.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exhibit Batch | 126228.423 | 142187.3625 | 158172.931 | 174139.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Raw Materials & Packaging materials
2.3702
Analytical Requirement
Reference Product Requirement
PHASE WISE BUDGET
BUDGET HEADS
lacs

## List
Product Type | Product type Factor | Manpower factor (Stability) | Capsule Size | Shell Price | Additional Charge for HCG Capsules | Dosage Form | Ref. | Batch size Units | Ref. | UOM | Ref. | Packing style | Filing Type | API Source | R&D Division (Location) | R&D Head | Project Manager | Plant Code |  | Group Leader |  |  |  |  | Analytical group leader | Packaging Cost | Packing Type | Ref. | Unit | Test Code + Test Description | Cost | Test code | Test Description
IR | 80 | 0.3 | Size 000 | 0.3 | 10000 | Solid Oral | 0 | Tablets | 2 | mg | 0 | Bottle | PI | In-house | EP11-INJ(H) | Pramanik Saugata | Vikram Rakshe | EP18-ONCO(H) | 850000 | Amod Dhabu | 1 | Patented | Yes | PI | Rohit Hirpara | 8.9 | HDPE 30 cc | 0 | Nos. | T001: Assay by HPLC | 1250 | T001 | Assay by HPLC | US (ANDA) Filing | 51 | Mr. Ramesh Pimple | Single dose_Two treatment_ cross-over_two period | Special Chemical | gm | 1
ER/DR/SR | 60 | 0.4 | Size 00 el | 0.3 |  | Liquid Oral | 1 | Capsules | 0 | meq | 1 | Blister | PII | Outsourced | EP12-API(H) |  |  | EP04-EOU(H) | 168000 | Dr. Ketan Savjani | 2 | Generic | No | PII | Munish Buch | 8.9 | HDPE 40 cc | 0 | Nos. | T002: Assay by HPLC (Double component in single chromatography) | 1500 | T002 | Assay by HPLC (Double component in single chromatography) | EU Filing | 45 | Mr. Santosh Savarkar | Single dose_Two treatment_ Parallel_One period | KH2PO4 | kg | 2
Pellets | 80 | 0.4 | Size 00 | 0.3 |  | Injectables | 2 | Liters | 1 | µg | 2 | Bottle and Blister | PIII |  | EP07-DOM(B) |  |  | EP10-SPD(H) | 700000 | Dr. Rushil Shah | 3 |  |  | PIII | Paresh Trivedi | 10 | HDPE 60 cc | 0 | Nos. | T003: Assay by HPLC (Triple component in single chromatography) | 1700 | T003 | Assay by HPLC (Triple component in single chromatography) | Canada | 23 | Mr. Ramesh Pimple | Single dose_Two treatment_ cross-over_two period_Truncation | Acetonitril | Lit | 3
Parenteral | 80 | 0.4 | Size 0 el | 0.3 | [5 empty] | mg/ml | 3 | Vials | PIV |  | EP20-AHD | Dr. Deepak Gondaliya | Akanksha Pandit | EP05-F2(P) |  |  | 4 |  |  | PIV | Bipin Patel | 10 | HDPE 75 cc | 0 | Nos. | T004: Assay by UV | 600 | T004 | Assay by UV |  |  |  | Single dose_Two treatment_ cross-over_Three_period_Partial Repliacte | Ethanol | Lit | 3
Granules | 80 | 0.4 | Size 0 | 0.3 | [5 empty] | mg/vial | 4 | Ampoules | PIV(NI) |  |  |  |  | EP09-API(KK) |  |  | 5 |  |  |  | Sanket Shah | 10 | HDPE 100 cc | 0 | Nos. | T005: Assay by GC | 2500 | T005 | Assay by GC |  |  |  | Single dose_Two treatment_ cross-over_Four_period_Full Repliacte | Hexane | Lit | 3
Transdermal patch | 80 | 0.4 | Size 1 el | 0.3 | [7 empty] | Infusion Bags | [5 empty] | EP16-DOM(J) | [6 empty] | Kamlesh Patel | 10 | HDPE 120 cc | 0 | Nos. | T006: Assay by Titrimetry | 750 | T006 | Assay by Titrimetry | Yes |  |  | Multiple dose studies | IPA | Lit | 3
|  |  | Size 1 | 0.3 | [13 empty] | Mehsana | [7 empty] | 10 | HDPE 150 cc | 0 | Nos. | T007: Assay by Ion Chromatography | 4000 | T007 | Assay by Ion Chromatography | No |  |  |  | Methanol | Lit | 3
|  |  | Size 2 el | 0.3 | [21 empty] | 10 | HDPE 180 cc | 0 | Nos. | T008: Dissolution Profile by HPLC | 4000 | T008 | Dissolution Profile by HPLC |  |  |  |  | Impurity-1 | mg | 4
|  |  | Size 2 | 0.3 | [21 empty] | 10 | HDPE 200 cc | 0 | Nos. | T009: Dissolution single point by HPLC | 2000 | T009 | Dissolution single point by HPLC |  |  |  |  | Impurity-2 | mg | 4
|  |  | Size 3 | 0.3 | [21 empty] | 11 | HDPE 250 cc | 0 | Nos. | T010: Dissolution Profile by HPLC 3 units | 2500 | T010 | Dissolution Profile by HPLC 3 units |  |  |  |  | Impurity-3 | mg | 4
|  |  | Size 4 el | 0.3 | [21 empty] | 11 | HDPE 300 cc | 0 | Nos. | T011: Dissolution Profile by HPLC 12 units | 8000 | T011 | Dissolution Profile by HPLC 12 units |  |  |  |  | Impurity-4 | mg | 4
|  |  | Size 4 | 0.3 | [21 empty] | 11 | HDPE 500 cc | 0 | Nos. | T012: Dissolution Profile by UV | 3000 | T012 | Dissolution Profile by UV |  |  |  |  | Impurity-5 | mg | 4
|  |  | Size 5 | 0.3 | [21 empty] | 11 | HDPE 1000 cc | 0 | Nos. | T013: Dissolution single point by UV | 1800 | T013 | Dissolution single point by UV |  |  |  |  | Impurity-6 | mg | 4
[26 empty] | 11 | HDPE 1500 cc | 0 | Nos. | T014: Dissolution Profile by UV 3 units | 900 | T014 | Dissolution Profile by UV 3 units |  |  |  |  | Assay Column | No. | 5
[26 empty] | 11 | HDPE 2000 cc | 0 | Nos. | T015: Dissolution Profile by UV 12 units | 6000 | T015 | Dissolution Profile by UV 12 units |  |  |  |  | Chiral Column | No. | 5
[26 empty] | 20 | HDPE 60 CC Heavy Weight | 0 | Nos. | T016: Dissolution profile by LCMS | 75000 | T016 | Dissolution profile by LCMS |  |  |  |  | Dissolution Column | No. | 5
[26 empty] | 3 | Silica canister (0.5g) | 0 | Nos. | T017: Dissolution single point by LCMS | 20000 | T017 | Dissolution single point by LCMS |  |  |  |  | GC Column | No. | 5
[26 empty] | 3 | Silica canister (1g) | 0 | Nos. | T018: Dissolution profile by titrimetry | 4500 | T018 | Dissolution profile by titrimetry |  |  |  |  | RS Column | No. | 5
[26 empty] | 4 | Silica canister (2g) | 0 | Nos. | T019: Dissolution profile by titrimetry 3 units | 2200 | T019 | Dissolution profile by titrimetry 3 units |  |  |  |  | Carrier Gas | No. | 5
[26 empty] | 15 | Silica canister (3g) | 0 | Nos. | T020: Dissolution single point by Titrimetry | 1200 | T020 | Dissolution single point by Titrimetry
[26 empty] | 2 | Silica bag (0.5g) | 0 | Nos. | T021: In-vitro release study (by Franz Diffusion) | 11000 | T021 | In-vitro release study (by Franz Diffusion)
[26 empty] | 2 | Silica bag (1g) | 0 | Nos. | T022: Method Development for Assay | 20000 | T022 | Method Development for Assay
[26 empty] | 3 | Silica bag (2g) | 0 | Nos. | T023: Method Development for dissolution | 22000 | T023 | Method Development for dissolution
[26 empty] | 15 | Silica bag (3g) | 0 | Nos. | T024: Method Development for RS | 25000 | T024 | Method Development for RS
[27 empty] | Oxy. Scavenger (10cc) | 0 | Nos. | T025: Method Development for residual Solvent | 10000 | T025 | Method Development for residual Solvent
[27 empty] | Oxy. Scavenger (20cc) | 0 | Nos. | T026: Related Substances (By TLC) | 1000 | T026 | Related Substances (By TLC)
[26 empty] | 1 | Filler | 1 | g | T027: Related Substances by HPLC | 2500 | T027 | Related Substances by HPLC
[26 empty] | 510 | Aluminium Foil (20µ) | 2 | kg | T028: Related Substances by GC | 3500 | T028 | Related Substances by GC
[26 empty] | 480 | Aluminium Foil (25µ) | 2 | kg | T029: Uniformity of dosage units by content uniformity | 2500 | T029 | Uniformity of dosage units by content uniformity
[26 empty] | 145 | PVC Foil (200µ) | 2 | kg | T030: Uniformity of Dosage units by weight variation | 200 | T030 | Uniformity of Dosage units by weight variation
[26 empty] | 145 | PVC Foil (250µ) | 2 | kg | T031: Uniformity of dosage unit by weight variation (Subdivision) | 200 | T031 | Uniformity of dosage unit by weight variation (Subdivision)
[26 empty] | 155 | PVC Foil (300µ) | 2 | kg | T032: Uniformity of dosage unit by content uniformity (Subdivision) | 3500 | T032 | Uniformity of dosage unit by content uniformity (Subdivision)
[26 empty] | 155 | PVC Foil (350µ) | 2 | kg | T033: Disintegration Time | 100 | T033 | Disintegration Time
[26 empty] | 225 | PVC/PVDC Foil (200/60) | 2 | kg | T034: Water Content (by KF) | 300 | T034 | Water Content (by KF)
[26 empty] | 255 | PVC/PVDC Foil (200/90) | 2 | kg | T035: Water content (by coloumetric) | 550 | T035 | Water content (by coloumetric)
[26 empty] | 225 | PVC/PVDC Foil (250/60) | 2 | kg | T036: Hardness | 300 | T036 | Hardness
[26 empty] | 255 | PVC/PVDC Foil (250/90) | 2 | kg | T037: Blend uniformity | 2500 | T037 | Blend uniformity
[26 empty] | 225 | PVC/PVDC Foil (300/60) | 2 | kg | T038: Microbial Limit Test | 4000 | T038 | Microbial Limit Test
[26 empty] | 255 | PVC/PVDC Foil (300/90) | 2 | kg | T039: Weight Variation | 200 | T039 | Weight Variation
[26 empty] | 230 | PVC/PVDC Foil (350/60) | 2 | kg | T040: Residual solvents | 2500 | T040 | Residual solvents
[26 empty] | 260 | PVC/PVDC Foil (350/90) | 2 | kg | T041: Acid resistance value | 3000 | T041 | Acid resistance value
[26 empty] | 285 | PVC/PE/PVDC Foil (250/30/60) | 2 | kg | T042: Identification by UV | 300 | T042 | Identification by UV
[26 empty] | 310 | PVC/PE/PVDC Foil (250/30/90) | 2 | kg | T043: Identification by HPLC | 300 | T043 | Identification by HPLC
[26 empty] | 1450 | PVC/Aclar Foil (250/51) | 2 | kg | T044: Identification (by TLC) | 1000 | T044 | Identification (by TLC)
[26 empty] | 1800 | PVC/Aclar Foil (250/71) | 2 | kg | T045: Identification test for Chemical | 600 | T045 | Identification test for Chemical
[26 empty] | 420 | Lidding foil (20µ) | 2 | kg | T046: pH | 200 | T046 | pH
[26 empty] | 400 | Lidding foil (25µ) | 2 | kg | T047: Loss on Drying | 300 | T047 | Loss on Drying
[30 empty] | T048: Particle size | 3000 | T048 | Particle size
[30 empty] | T049: Melting Point Range | 200 | T049 | Melting Point Range
[30 empty] | T050: Solubility (mg/ml) | 3000 | T050 | Solubility (mg/ml)
[30 empty] | T051: X-ray Diffraction (XRD) | 1200 | T051 | X-ray Diffraction (XRD)
[30 empty] | T052: SEM Analysis | 6000 | T052 | SEM Analysis
[30 empty] | T053: Acidity | 300 | T053 | Acidity
[30 empty] | T054: Alkalinity | 300 | T054 | Alkalinity
[30 empty] | T055: Tapped Density | 300 | T055 | Tapped Density
[30 empty] | T056: Untapped Density | 250 | T056 | Untapped Density
[30 empty] | T057: Specific Optimal Rotation | 400 | T057 | Specific Optimal Rotation
[30 empty] | T058: Chiral Purity | 4500 | T058 | Chiral Purity
[30 empty] | T059: Particulate matter | 200 | T059 | Particulate matter
[30 empty] | T060: Surface Tension | 3000 | T060 | Surface Tension
[30 empty] | T061: Viscosity | 1100 | T061 | Viscosity
[30 empty] | T062: Buffer Capacity | 900 | T062 | Buffer Capacity
[30 empty] | T063: Colour and clarity | 600 | T063 | Colour and clarity
[30 empty] | T064: Clarity and completeness of solution | 600 | T064 | Clarity and completeness of solution
[30 empty] | T065: Weight Loss | 200 | T065 | Weight Loss
[30 empty] | T066: Density | 250 | T066 | Density
[30 empty] | T067: Weight per ml | 200 | T067 | Weight per ml
[30 empty] | T068: Specific Gravity | 200 | T068 | Specific Gravity
[30 empty] | T069: pH of reconstituted solution | 200 | T069 | pH of reconstituted solution
[30 empty] | T070: Absorbance at 420 nm | 600 | T070 | Absorbance at 420 nm
[30 empty] | T071: %T @ 650nm | 600 | T071 | %T @ 650nm
[30 empty] | T072: Osmolality | 200 | T072 | Osmolality
[30 empty] | T073: Reconstitution time | 200 | T073 | Reconstitution time
[30 empty] | T074: Inductive Coupled Plasma (ICP) | 2200 | T074 | Inductive Coupled Plasma (ICP)
[30 empty] | T075: Sterility | 1400 | T075 | Sterility
[30 empty] | T076: Biological Asssay | 15000 | T076 | Biological Asssay
[30 empty] | T077: Uniformity of dispersion | 200 | T077 | Uniformity of dispersion
[30 empty] | T078: Alcohol content | 3500 | T078 | Alcohol content
[30 empty] | T079: Reduced Pressure measurement inside vial | 200 | T079 | Reduced Pressure measurement inside vial
[30 empty] | T080: Swelling Index | 600 | T080 | Swelling Index
[30 empty] | T081: Bacterial Endotoxins | 4000 | T081 | Bacterial Endotoxins
[30 empty] | T082: Aggregation Study | 3000 | T082 | Aggregation Study
[30 empty] | T083: TEM Analysis | 25000 | T083 | TEM Analysis
[30 empty] | T084: Syringibility | 200 | T084 | Syringibility
[30 empty] | T085: Droplet Size | 6000 | T085 | Droplet Size
[30 empty] | T086: Zeta Potential | 750 | T086 | Zeta Potential
[30 empty] | T087: Fine Particle by NG Impactor | 15000 | T087 | Fine Particle by NG Impactor
[30 empty] | T088: Fine Particle by AG Impactor | 2800 | T088 | Fine Particle by AG Impactor
[30 empty] | T089: % Entrappment (HPLC) (For Depot) | 1700 | T089 | % Entrappment (HPLC) (For Depot)
[30 empty] | T090: Free Drug (For Doxo) | 1900 | T090 | Free Drug (For Doxo)
[30 empty] | T091: Volume in Container | 200 | T091 | Volume in Container
[30 empty] | T092: Extractable Volume | 200 | T092 | Extractable Volume
[30 empty] | T093: Filled Volume | 200 | T093 | Filled Volume
[30 empty] | T094: Conductivity | 200 | T094 | Conductivity
[30 empty] | T095: Uniformity of deliver dosage or entire content | 5400 | T095 | Uniformity of deliver dosage or entire content
[30 empty] | T096: Friability | 75 | T096 | Friability
[30 empty] | T097: Water Activity | 5000
[30 empty] | T098: Method Validation | 700000

## RACI (hidden)
Process-> | Person nominated for CFT | Project initiation | Literature review | Planning | Purchase/ Sourcing | Formulation development | Impurity isolation/ sourcing | Analytical development | WRS | CMV/CMD | Scale-up | Pilot BE | Specs | AMV and AMT | Exhibit | Stability | Pivotal BE | Filing | Closure
Department
FD | Group Leader | R | R | R | A | R&A | A | A | I | A | R | A | R | A | R | C | A | R | C
ADL | Group Leader | R | R | R | A* | R | R | R&A | R | R | R | R | R | A | R | I | R | R | C
AMV | Group leader |  | I | R | I | I | I | I | R | I | I |  | I | R | I | I |  | A | C
Purchase | Kumat | R | I | R | R | C | R | I | R* | I | R |  | A* | A* | I | I |  | A | C
R&D QA | Group Leader | R | I | R | A* | C | C | C | A | A | A | C | A | A | A | I | C | A | C
IP team | Nishid/ GL | R | R (API) | R | C* | C | C | I |  | I | C |  | I | I | C | I |  | R | C
RA | TBD | R | A | R | A* | C | C | C |  | I | C | R | A | C | C | C | R | R | C
PDC | Ajay Bapat | I | I | R | C | A |  | I |  | C: A; C: A; R: I; C: C
Plant TT | TT Incharge | I |  | R | I | C |  |  |  | R | R |  |  | I | R | I |  | A | C
BE | Rosi Reddy | I | R | R |  | I | I |  |  |  |  | R |  |  | I | I | R | C | C
Plant QA | (TBN)Jayashree Nair | I |  | C | I | I |  |  |  | A | C |  | I | A | R&A | A | A | R | C
Plant QC | (TBN)Jayashree Nair | I |  | C | I | I |  | I |  | R | C |  | C | R | R | R | R | A | C
Production | (TBN)Milind Lad | I |  | C | I | I |  |  |  | A | R |  | C | I | R | I | I | A | C
Plant purchase | (TBD) Mani/Malwadkar | I |  | C | C | I |  |  |  | I | C |  | I | I | A | I |  | A | C
Project management | TBD (Jayant/Mahesh) | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | R&A
Legend | R | Responsibility
| A | Accountability
| C | Consult
| I | Inform
| TBD | To be determined
NOTE | Responsibilty: It is indicated against a department which actually carries out that process
Accounatability: It is indicated against a department which is answerable for the correct and thorough completion of the process
Consulted: It is indicated against a department whose advise is critical for ensuring successful outcome of the process
Informed: It is indicated against a department which should be infomed that a particular process is under execution
* Marked Cells
F8 | Outsourcing API
F7 | In case of Audit needed
F9 | RA/QA decide on vendors
N6 | Excipients/ Limits/Outsourced API etc
J6 | Applicable if WRS sourced from outside
O6 | Applicable in case of additional puchase requirement
F4 | Accountability for analytical related sourcing