## 1.PMO_BD
To be filled by PMO before forwarding to Group Leaders
General
Project Name |  | Please follow a standard format-" Molecule_Market"
Market |  | Ex-US/EU/UK/CAN/ROW/IND- In case of multiple markets please specify
Sponsor/Business Partner |  | Ex- Input Emcure if product to be commercialised inhouse
API Market Price ($ Per KG)
Target Cost($ Per KG)
Market Details
Sales (USD Mn) |  | Input latest sales data of drug product from IMS
Number of Competitors |  | Ex-Input number of approved DMF sources for US market
Annual Volume Kg(20% of market Share) |  | Input total API consumption from IMS
Formulation Details
Product Type |  | solid oral /Injection -- Dropdown
No Of Strength
To be discuused with Formulations Group leader to arrive at Api quantities below
Formulation Quantity Required in kg/gm
Stage
Development
Scale-up
Exhibit
Total
IP Status
Intellaecteual Property Information | Patent Tab tobe provided nby ambike

## 2.GL-INIT (hidden)
To be filled by API Group Leader before project initiation
Project Name
Market
Project Initiation Date
R&D Division
API Group Leader
Project Complexity | On a scale of 1 to 5 with 1 being least complex
Date for submission of Project budget and timeline summary | Please note that budget for projects are limited during feasibility period
Budget for Feasibility
Manhours Rate
PRD Man Hours
ARD Man Hours
Total Manhour
Total Cost of Manhours
Raw Material Cost(INR) | Cost of Raw Material
Cost of Analytical (INR) | Cost of Columns/Standards Etc
Total Cost of Feasibility

## 3.PIF (hidden)
API Project Initiation Form/Code Creation
Project Name |  |  |  | Project start date
Administrative section |  |  |  | Commercial section
1 | Sponsor/Business Partner |  |  | 1 | Market
2 | R&D Division |  |  | 2 | Market size (USD Mn)
3 | Group Leader |  |  | 3 | No of Players
4 | Complexity |  |  | 4 | Emcure Annual API requirement
Project Section
1 | Business Rationale
2 | Initial Scope and Objectives
3 | Target date for completing milestone planning and filling up project summary template*
4 | Feasibility Budget
This form needs to be filled within two days of project allocation to R&D
Note
[*]- Final allocation of budget will be made on approval of Project Charter Summary
Dr Gorakh Yellol |  | Dr Abhijit Roychowdhury | Dr Parag Gatne |  |  | Dr M K Gurjar
Group Leader |  | Director - API R&D | GM-PM |  |  | CSO

## 4.Project Summary Template
Project Charter Summary Template
Project Name |  |  |  | Time Lines I n Months
Market |  |  |  | Feasibility study | 3
Project Initiation Date | 2022-08-01 |  |  | Development | 2
Project End Date | calender date |  |  | Scale/up | 2
API Group Leader | text box |  |  | Validation | 4
Project Complexity | dropdown | 1,2,3,4,5 |  | Stability | 6
Finance Rates |  |  |  | Filing | 0.5
Manhour rate | 1400 | text box |  | Total | 17.5
Analytical Departments | ARD | Impurity | Stability | AMV | AMT
Chemicals/ Reagents | 2 | 2 | 2 | 2 | 2
No of Columns | 2 | 2 | 2 | 2 | 2
Cost per Column | 2 | 2 | 2 | 2 | 2
Total Cost of Coloumn | 4 | 4 | 4 | 4 | 4
Cost of Impurities/RLD/Standard/Silica | 2 | 2 | 2 | 2 | 2
Total Cost Of Analytical Rawmaterial | 8 | 8 | 8 | 8 | 8
PRD Department | Raw Material Cost
Development | 3
Optimization | 3
Scale Up | 3
Validation | 0
Total Cost Of Raw material | 9
Capital and Other Expenditure | Amount | Remark
Capex | 2
Other expenses/Utility Cost | 3
DMF / CEP Filing Cost | 4
Litigation/ Patent Cost | 5
Toxicity Study | 6
Manhour Estimates | No Of Employees | Months | Hours | Cost
PRD Department | 2 | 18 | 6336 | 8870400
Analytical Development Departments | 3 | 4 | 2112 | 2956800
Analytical Validation Department | 2 | 5 | 1760 | 2464000
Analytical Meathod Transfer Department | 1 | 6 | 1056 | 1478400
Impurity Department | 3 | 7 | 3696 | 5174400
Stability Department | 2 | 8 | 2816 | 3942400
Technology Transfer Department | 3 | 9 | 4752 | 6652800
Total Cost Of Man Hours |  |  | 22528 | 31539200
Head-Wise Budget (in Lacs) | Rupee (In Lac)
Total Cost Of Analytical Rawmaterial | 40
Total Cost Of Rawmaterial | 9
Total Cost Of Man Hours | 31539200
Capex | 2
Other Expenses/ Utility Cost | 3
Litigation cost /Patent Registration Cost/ Toxicity study | 5
DMF Filing Cost | 4
Bio Cost | 6
Total API Project Cost | 31539269
|  | Dr M K Gurjar |  | Mr.Sanjay Mehta
Dr Abhijit Roychowdhury | Dr Parag Gatane
API R&D | Project management | CSO |  | President Commercial

## 5.MSP Tracker (hidden)
S.N. | Activity | Responsibility | Dependencies (Predecessor) |  |  |  |  | Dependencies (Successor) |  |  |  | Duration in days | Start Date | End Date
Project Initiation
1 | Kick off | PM | - | - | - | - | - | 2 | 3 | 5 | 6 | 1
2 | Literature Search update, IPD clearance | R&D, IPD | 1 | - | - | - | - | 4 |  |  |  | 25
3 | PIF, BD code and eProject maping | PM, Finance | 1 | - | - | - | - | 4 |  |  |  | 1
4 | RM Quotation Columns & Std procurement, RM procurement | R&D, ARD, Purchase | 2 | 3 | - | - | - | 7 |  |  |  | 45
5 | Acquire test license/ Generate project/product code | RA, QA | 1 | - | - | - | - | 7 |  |  |  | 21
6 | IPD statement on Route/Polymorph | IPD | 1 | - | - | - | - |  |  |  |  | 20
Process & Analytical Feasibility
7 | Experiments for feasibility | R&D | 4 | 5 |  |  |  | 8 |  |  |  | 80
8 | RM, IM & API sample Submition to ARD | R&D | 7 |  |  |  |  | 9 |  |  |  | 10
9 | Tentative Analytical development for IM & IP | ARD | 8 |  |  |  |  | 11 | 13 | 16 |  | 30
10 | MFH for NI, Cost, DMF Filing & Safety | PM, R&D, ARD, RA | 7 | 9 |  |  |  | 11 | 18 |  |  | 2
Process & Analytical Optimization
RM Draft spec preparation
11 | Procurement of RM impurities & column | R&D, ARD, Purchase | 9 | 10 |  |  |  | 12 |  |  |  | 30
12 | RM method development if not suitable, RM Draft spec compliance from vendor | purchase | 11 | [8 empty] | 15
API Draft spec preparation
13 | Impurities synthesis & submition to Imp-lab | imp | 9 |  |  |  |  | 14 |  |  |  | 30
14 | Impurity Characterization | imp | 13 |  |  |  |  | 15 |  |  |  | 10
15 | Impurity submission with COA to ARD | imp | 14 |  |  |  |  | 16 |  |  |  | 5
16 | Analytical Method optimization for API Draft Spec & MOA preparation | ARD | 9 | 15 |  |  |  | 17 |  |  |  | 30
17 | API Indicative stability initiation | R&D STABILITY | 16 | [8 empty] | 180
Process optimization
18 | Experiments for optimization | R&D | 10 | 16 | [7 empty] | 15
19 | RMix, IM samples Submition to ARD | R&D ARD | 18 |  |  |  |  | 20 |  |  |  | 15
20 | Analytical Method optimization for IP & IM | ARD | 19 |  |  |  |  | 21 |  |  |  | 20
21 | IP & IM Draft spec preparation | ARD | 20 |  |  |  |  | 22 |  |  |  | 10
Process and Spec Approval
Trend Batches execution
22 | Stage-1,2,3 preparation | R&D | 21 |  |  |  |  | 23 | 24 |  |  | 20
23 | Draft process with TI-sheets to QA | R&D QA | 22 |  |  |  |  | 25 |  |  |  | 10
24 | Draft spec of RM, IP, IM & API to QA | ARD QA | 22 |  |  |  |  | 25 | 26 | 37 |  | 10
QA approval of Process, Spec & AVL
25 | QA approval for Process, RM, IP & IM Spec | QA | 23 |  |  |  |  | 31 | 39 | 40 |  | 10
26 | QA approval for API spec | QA | 23 | 24 | [7 empty] | 7
27 | AVL compilation CCF initiation | PURCHASE QA | 24 |  |  |  |  | 28 |  |  |  | 10
28 | Vendor Audit (if Rerquired), compliance | Compliance cell Purchase | 27 |  |  |  |  | 29 |  |  |  | 0
29 | CCF approval , AVL Approval, communicated to plant | plant QA R&D QA | 28 |  |  |  |  | 66 |  |  |  | 3
Stability
30 | Intermediate / API stability initiaton | stability dept | 22 | [8 empty] | 180
WRS qualification
31 | Submition of all std with COA | ARD AMV QA | 25 |  |  |  |  | 32 |  |  |  | 7
32 | WRS qualification and submission to plant | ARD QA | 31 |  |  |  |  | 36 | 56 |  |  | 7
CMV
33 | Equip. cleaning process & Spec QA approval | ARD QA | [5 empty] | 34 |  |  |  | 3
34 | CMV protocol preparation and QA approval. | PLANT QA | 33 |  |  |  |  | 35 |  |  |  | 3
35 | C M Validation | PLANT QA | 34 |  |  |  |  | 36 |  |  |  | 22
Scale-up
36 | CFT | TT | 32 | 35 | [7 empty] | 1
37 | RM procurement for scale-up | TT PURCHASE | 24 |  |  |  |  | 38 |  |  |  | 30
38 | RM analysis | ARD | 37 | [8 empty] | 3
39 | Preparation and approval of scale-up BMR & protocol | TT QA | 25 |  |  |  |  | 41 |  |  |  | 2
40 | Preparation & approval of ECR | PLANT QA | 25 |  |  |  |  | 41 |  |  |  | 2
41 | Execution of scale up batch, Complete analysis, BMR review & stability initiation | TT PLANT | 39 | 40 |  |  |  | 42 |  |  |  | 30
42 | Scale-up report by TT | TT QA | 41 |  |  |  |  | 42 |  |  |  | 7
TTP, LDR preparation & CFT
43 | TTP preparation | R&D QA | 42 |  |  |  |  | 44 |  |  |  | 10
44 | LDR preparation | R&D QA | 43 |  |  |  |  | 45 |  |  |  | 10
45 | LDR review by QA | QA | 44 |  |  |  |  | 46 |  |  |  | 10
46 | TTP QA approval & submition to plant | QA | 45 |  |  |  |  | 47 | 60 |  |  | 5
47 | CFT for Validation | TT | 54 | [8 empty] | 2
AMV & AMT
48 | Prepation of Validation protocol for IM, SM, DS | AMV | 32 |  |  |  |  | 49 |  |  |  | 10
49 | Protocol review and approval | AMV QA | 48 |  |  |  |  | 50 |  |  |  | 15
50 | Execution of validation activity. | AMV | 49 |  |  |  |  | 51 |  |  |  | 45
51 | AMV data review, report preparation and submission for approval | AMV QA | 50 |  |  |  |  | 52 |  |  |  | 10
52 | AMV report review and approval by QA | QA | 51 |  |  |  |  | 53 |  |  |  | 10
53 | Revision in specs and MoA | ARD | 52 |  |  |  |  | 54 |  |  |  | 7
54 | AMT protocol preparation and approval | AMV QA PLANT QA - QC | 53 |  |  |  |  | 55 |  |  |  | 4
55 | Protocol execution at both transferring and receiving laboratories | AMV QA PLANT QA - QC | 54 |  |  |  |  | 56 |  |  |  | 7
56 | AMT report by plant QC | AMV QA PLANT QA - QC | 55 |  |  |  |  | 57 |  |  |  | 3
57 | specs from spec cell to plant | ARD QA SPEC CELL | 56 |  |  |  |  | 63 |  |  |  | 4
Validation
58 | RM procurement for vaildation batches | TT PURCHASE | 29 |  |  |  |  | 64 |  |  |  | 30
59 | Creation of item codes (Intermediate, packing material and miscellaneous) | PLANT QA | 29 | [8 empty] | 3
60 | Preparation and approval of validation BMR | PLANT QA | 46 |  |  |  |  | 61 | 65 |  |  | 2
61 | Creation of BOM | PLANT QA | 60 |  |  |  |  | 62 | 65 |  |  | 1
62 | Preparation and approval of ECR | QA PLANT | 61 |  |  |  |  | 65 |  |  |  | 1
63 | Preparation of specs and approval | PLANT QC QA | 57 |  |  |  |  | 65 |  |  |  | 2
64 | RM PM analysis | PLANT QC | 58 |  |  |  |  | 65 |  |  |  | 3
65 | Executiion of 3 validation batches | PLANT QA | 60 | 61 | 62 | 63 | 64 | 66 |  |  |  | 60
66 | Analysis and release of Validation batches (micro if reqd.) | QC QA | 65 |  |  |  |  | 67 |  |  |  | 8
67 | Final NI analyisis | R&D IPD | 66 |  |  |  |  | 68 |  |  |  | 0
68 | Validation report preparation and approval | PLANT QA | 67 |  |  |  |  | 69 | 70 |  |  | 3
69 | Dispatch to ANDA holder | PLANT | 68 | [8 empty] | 5
Stability
70 | Stability study protocol preparation | QC QA | 68 |  |  |  |  | 71 |  |  |  | 5
71 | Stability study protocol approval | QA | 70 |  |  |  |  | 72 |  |  |  | 5
72 | Stability sample packing | QC QA | 71 |  |  |  |  | 73 |  |  |  | 2
73 | Validation batch sample charged for stability | QC QA | 72 |  |  |  |  | 74 |  |  |  | 2
74 | 3 month stability study, data review and approval | QC QA | 73 |  |  |  |  | 75 |  |  |  | 100
DMF filing
75 | Documents from R&D QA and plant QA | R&D QA PLANT QA | 74 |  |  |  |  | 76 |  |  |  | 7
76 | Check for adequacy of documents and information | RA | 75 |  |  |  |  | 77 |  |  |  | 7
77 | Compilation of dossier in CTD format | RA | 76 |  |  |  |  | 78 |  |  |  | 7
78 | DMF filing | RA | 77 | [8 empty] | 1

## 6.IPD (hidden)
Project Name | 0
Market: | 0
Generic Status: |  |  | Y/N
Type of Filing: |  |  | Ex: PIV/PIII/PII/PIV(NI)/F2F
Earliest Market Entry Date:
No. of approved DMFs:
No. of DMFs applcations pending approval:
Legal Status(Litigation):
Cost of Litigation
IPD Comments:
*Patents No. | Original Expiry Date (dd-mmm-yy) | Type (Subs, Form, MOA, MOT Etc) | Extn Applcation (Y/N) | Expiry Date on Extn | Comments (Patent Specific) | Strategy
*Please include new patents under consideration
Insert rows if required
Exclusivity Type | Expiry | Strategy

## 7.Go-No-Go (hidden)
Project Closure Form
Project name | 0 |  | Project start date | #REF!
Project SAP Code | #REF!
Commercial
Technical
# This form is to be filled in the event project is discontinued after feasibility phase
0 |  |  |  |  | (Dr.Mukund Gurjar)
Group Leader | Departmental Head | Project Management |  |  | CSO