## DeliveryPlan
Project Name | Emcure NPD (Phase 2 - Milestone 1) |  |  | Project Manager |  | Nilesh Jain
Start Date | 2023-07-19 | End Date | 2023-11-24 | Overall Progress |  | 18%
Activity | Sub Activity | Epic | Start Date | End Date | Status | Progress | Remark
Phase 2 - Milestone 1 |  |  | 2023-07-19 | 2023-11-24
CR-2 | This contains all the feedback / change request, we received from Emcure team during Milestone - 1 UAT meetings. Note: There were couple of points which were minor enhancement, we have not included in this into CR-2, We have already completed and published to UAT |  | 2023-07-19 | 2023-08-04 | Completed | 100%
Execution
CR-3 |  |  |  |  | In Progress | 1%
| P1 | Epic 1 | 2023-08-07 | 2023-09-08 | In Progress | 0%
| P2 | Epic 2 | 2023-09-11 | 2023-10-06 | Yet to start | 0%
Execution
CR-4 | Migration of all the Existing PIDF which is maintained in excel file right now. (P3) | Epic 3 | 2023-10-09 | 2023-11-03 | Yet to start | 0%
Execution
UAT | UAT for CR-3 & 4 |  | 2023-11-06 | 2023-11-24 | Yet to start | 0%
Phase 2 - Milestone 2 | [6 empty] | Yet to identified