## IPD
IPD
| Patent Strategy | Wait for expiry | Develop around | Limit SmPC / Carve out | Litigation | Negotiation | Dropdown
|  | Others | If others give text box
Patent Type
| Basic Patent Expiry | Other Limiting Patent Date 1 | Other Limiting Patent Date 2 | Earliest Launch Date
Country | Date | Date | Date | Date
| Any patents to be filed |  |  | Yes/No
| Earliest market entry |  | Date | Validation to be kept or not
| Estimated Number of generics in the market |  | Count and Names | As and when data is available - optional
|  | Law firm being used |  | As and when data is available - optional

## RnD
RnD General Section | R&D Responsible person | name |  |  |  | API Management
RnD General Section | Type of development | Date from IP Tab |  |  |  | API Outsource |  |  |  | API Rnd & Charter (Readonly)
[6 empty] | API suppliers | Primary | Potential Alt. 1 | Potential Alt. 2 | API if In-house
API Management | API Supplier | =J3 | =J4 | =J5 |  | Supplier |  |  |  | Root of Synthesis
[6 empty] | Polymorph |  |  |  | Polymorph
RnD General Section | Pivotal batches manufactured completed | Date | Cost ($) |  |  | Process (early c) |  |  |  | Process (early c)
RnD General Section | Stability Results |  |  |  |  | Process (late c) |  |  |  | Process (late c)
RnD General Section | Day 0 | Date | Estimate 1st date to be 1 month after C5 |  |  | Manufacturing site |  |  |  | Manufacturing site
RnD General Section | 3 months | Date | Estimate 1st date to be 3 months after C6 |  |  | Date of Site EU authority inspection | From Quality | From Quality | From Quality | Scheduled
RnD General Section | 6 months | Date | Estimate 1st date to be 3 months after C7 |  |  | Date of Site Tillomed inspection | From Quality | From Quality | From Quality | Filing time
[6 empty] | Lead time |  |  |  | Investments/Capex if Any
Clinical Tab | BE Study Results | Date from Bio Tab |  |  |  | DMF availability |  |  |  | Lead time
[6 empty] | Cost (R&D cost/KG) |  |  |  | Cost (R&D cost/KG)
RA Tab | Last date to Regulatory | Date | Estimate 1st date to be 1 month after C9 |  |  | Cost (commercial cost/KG) |  |  |  | Cost (commercial cost/KG)
[7 empty] | textboxes | textboxes | textboxes
RnD General Section Readonly data | Pack sizes on stability | Pack size 1 | Pack size 2 | Pack size 3 | Pack size n
RnD General Section Readonly data | Strength 1 | Types | Types | Types | Types
RnD General Section Readonly data | Strength 2 | Types | Types | Types | Types
RnD General Section Readonly data | Strength 3 | Types | Types | Types | Types
RnD General Section Readonly data | Strength n | Types | Types | Types | Types

## Formulation
TDP Section | Formulater Responsible person | name |  | Optional to decide with PM
TDP Section | Approach | QnQ formulation vs the innovator or are we changing the formulation/ Design around to avoid the patent | [7 empty] | From Patent TAB
TDP Section | TDP | Innovator |  |  | Emcure
| Strength | x mg | y mg | z mg | x mg | y mg | z mg
Description:
Shape
Colour
Engraving
| Packaging |  | PICTURE |  |  | PICTURE |  | Need to upload image
Primary
Secondary
Shelf-life
Storage / Handling
On Hold for now, we will have this in milestone 2 & we will keep this in commercial module | Estimated Annual Volume
| Calculated from country tabs | Xmg | ymg | Zmg |  |  |  |  | pack size * Units * country = Tablets per year
Year 1
Year 2
Year 3
General Section / Optional Not Mandatory | Non-standard product | Yes / No
General Section / Optional Not Mandatory | Pivotals
General Section / Optional Not Mandatory | Batch size
General Section / Optional Not Mandatory | No. Batches per strength
General Section / Optional Not Mandatory | Site transfer (if yes, when) | Date
General Section / Optional Not Mandatory | API ordered | Date
General Section / Optional Not Mandatory | API Received | Date
Formulation team could have extra milestones here if required
General Section / Optional Not Mandatory | Final Formulation Approved | Date

## RA
Pivotal batch manufactured | Date from R&D Tab | Country wise
Last data from R&D | Date from R&D Tab | Country wise
BE Final Report | Date from Bio Tab | Country wise
List of countries |  | Country wise
Type of Submission | DCP, CP, RUP, National, MRP | Country wise
Dossier Ready Date | Date | Country wise
Earliest Submission - D Excl |  | Country wise
Earliest Launch - D Excl | From patent tab | Country wise

## Tillomed in-house Plan
Id | Task | Start Date | EndDate | Dependency | Tab that data comes from | Name of field(s)
1 | Development Phase |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0 | Formulation TDP | API ordered + API Received
3 | Select API suppliers | Formulation TDP(API Received)+3 MONTHS | Formulation TDP(API Received)+3 MONTHS +1 Day | 2 | Formulation TDP
4 | Formulation Finalised | D4 + 3months | C5 + 1 day | 3 | Formulation TDP | Final Formulation Approved
5 | Manufacture Pivotal batches | D5 + 1month | C6 + 7 days | 4 | R&D | Pivotal Batches Manufactured Completed
6 | Test and Place on Stability | D6 + 1 day | C7 + 1 month | 5 | R&D | D7 = Day 0
7 | Carry out Biostudy | D7 + 3 months | C8 + 2 months | 6 | Biostudy | D8 = Date Of Final Report
8 | 3 month stability Report | D7 + 4 months | C9 | 6 | R&D | D9 = 3 months
9 | 6 month stability Report | C9 + 3 months | C10 | 8 | R&D | D10 = 6 months
10 | Give last data to RA | the latest of D7 + D10 + 1 month | C11 | 7+9 | R&D | D11 = Last Data To Regulatory
11 | Regulatory Phase | D11 | D46 or D48 whichever is latest | 10
12 | Dossier Ready Date | D11 + 1month | C13 | 10 | RA | Dossier Ready Date
13 | Submit DCP in interested EU countries - DCP1 | d13 + 7 days | C14 | 12 | RA | DCP submission date
14 | RA Submission Dues Paid into Germany | D14 | D14 + 1 days | 13 | RA | Submission dues paid
15 | RA Submission Dues Paid into France | D14 | D14 + 1 days | 13 | RA | Submission dues paid
16 | RA Submission Dues Paid into Italy | D14 | D14 + 1 days | 13 | RA | Submission dues paid
17 | Submit DCP in interested EU countries - DCP2 | If required same timelines as DCP1 but different start date |  | 10 | RA
18 | Submit DCP2 into Germany | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13 | RA | Submission Dues Paid
19 | Submit DCP2 into France | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13 | RA | Submission Dues Paid
20 | Submit DCP2 into Italy | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13 | RA | Submission Dues Paid
21 | Submit into Nationals |  |  |  | RA
22 | Submit Nationals into UK | D13 + 28 days | C23 | 12 | RA | National submission date
23 | Submit Nationals into Israel | D13 + 90 days | C24 | 12 | RA | National submission date
24 | DCP Validation |  |  |  | RA
25 | Validation DCP1 into Germany | D15 | C26+14 Days | 14 | RA | Country validation date
26 | Validation DCP1 into France | D15 | C27+14 Days | 15 | RA | Country validation date
27 | Validation DCP1 into Italy | D15 | C28+14 Days | 16 | RA | Country validation date
28 | Validation DCP2 into Germany | RA(Validation Date) | RA(Validation Date)+14 Days | 18 | RA
29 | Validation DCP2 into France | RA(Validation Date) | RA(Validation Date)+14 Days | 19 | RA
30 | Validation DCP2 into Italy | RA(Validation Date) | RA(Validation Date)+14 Days | 20 | RA
| DCP Procedure | C33 | D35 |  | RA
31 | DCP Starts | the latest of D29, D30, D31 + 1 day | C33 | 25, 26, 27 | RA | Day 0
32 | DCP Day 105 | D33 + 105 Days | C34 | 31 | RA | Day 105
33 | DCP Day 106 | D34 + file coefficient (Red, Orange, Green) | C35 | 32 | RA | Day 106
34 | DCP End of Procedure (EOP) | D35 + 104 days | C36 | 33 | RA | EOP)
35 | UK Validation | D23 | C37+14 Days | 22 | RA
36 | Israel Validation | D24 | C38+14 Days | 23 | RA
37 | Submit Nationals in other interested countries | D13 + |  | 12 | RA
| Pharmacovigilance requirements | D13 + 90 Days | C36 - 1 month | 12 | Pharmacovigilance | Pharmacovigilance requirements
38 | National Phase in Germany | D36 | C41 + German Coefficient from DCP in months on master country | 34 | RA | Between EOP and German Approval
39 | DCP Approval in Germany | D41 | C42 | 38 | RA | Germany Approval
40 | National Phase in France | D36 | C43 + France Coefficient | 34 | RA | France Phase
41 | DCP Approval in France | D43 | C44 | 40 | RA | France Approval
42 | National Phase in Italy | D36 | C45 + Italy Coefficient | 34 | RA | Italy Phase
43 | DCP Approval in IT | D42 | C46 | 40 | RA | IT Approval
44 | Approval in UK | D37+UK coefficient from national in months on master country | C47 | 35 | RA | UK
45 | Approval in Israel | D38 + country coefficient | C48 | 36 | RA | Israel
Phase 4 Pre Launch Preparation per country
47 | Purchase order raised UK | 12 months before D77 | C50 | 74 | Country | UK
48 | Purchase order raised Germany | 12 months before D74 | C51 | 71 | Country | Germany
49 | Purchase order raised Italy | 12 months before D76 | C52 | 73 | Country | Italy
50 | Purchase order raised France | 12 months before D75 | C53 | 72 | Country | France
51 | API ordered UK | D50 + 14 days |  | 50 | Operations | UK
52 | API ordered Germany | D51 + 14 days |  | 51 | Operations | Germany
53 | API ordered Italy | D52 + 14 days |  | 52 | Operations | Italy
54 | API ordered France | D53 + 14 days |  | 53 | Operations | France
55 | Cutter Guides sent to Artwork | D36 - 1 month | C58 | 34 | Operations | Cutter Guides sent to plant
56 | Draft Artworks completed | D58 + 25 Days | C59 | 58 | Artwork | Artworks completed
57 | Artworks submitted and approved | D59 + 6 Days | C60 | 59 | Artwork | Artworks submitted and approved
58 | Plan Batch manufacture | First Approval either D42, D44, D46, D47, D48 | C61 + 14 Days | 39, 41, 43, 44, 45 |  | Batch manufacture
| Phase 5 Launch Activities per country |  |  |  |  | country Launch
60 | Final Artworks sent to plant | C64 - 1 month |  |  | Artwork | Date sent to plant
61 | Packaging for launch stock ordered | C65 - 2 months | C64 | 62 |  | Packaging for launch stock ordered
62 | Manufacture Launch Bulk Stock | First Approval either D42, D44, D46, D47, D48 Depending on country | C61 + 14 Days | 39, 41, 43, 44, 45 | Operations | Launch Bulk Stock Manufactured
63 | Approve Bulk product | C65 | D65 + 28 Days | 62 | Quality | Approve Bulk Product
64 | Packaging for launch stock received | D64 + 60 Days |  | 61 | Operations | Packaging for launch stock received
65 | Launch Bulk packed | C65 | D65 + 21 Days | 62, 64 | Operations | Launch Bulk packed
66 | Approve Finished product | D68 | D68 + 14 Days | 65 | Quality | Approve Finished product
67 | Send product to Europe | D69 | C70 + 28 Days | 66 | Logistics | "Plant dispatch date" to "Arrival Port in EU"
68 | Release product in Europe | D70 | C71 + 14 Days | 67 | Quality | Release Finished Product
69 | Send product to Country | D71 | C72 + 3 Days | 68 | Logistics | "Despatch Date in EU" to "Arrival in country"
70 | Obtain Price in Country | Approval in Country | Depends on country | 41, 43 | Country Tabs | Country Price
71 | Launch in Country Germany | 4 months after approval - D42 | C74 | 39 | Germany Country | Launch date
72 | Launch in Country Italy | 4 months after approval - D44 | C75 | 41 | Italy Country | Launch date
73 | Launch in Country France | 4 months after approval - D46 | C76 | 43 | France Country | Launch date
74 | Launch in Country UK | 4 months after approval - D47 | C77 | 44 | UK Country | Launch date
75 | Launch in Country Israel | 4 months after approval - D48 | C78 | 45 | Israel Country | Launch date

## Tillomed in Phase
Id | Task | Start Date | EndDate | Dependency | Tab data comes from
1 | Phase 2 Development |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0
3 | Select API suppliers | Formulation TDP(API Received)+3 MONTHS | Formulation TDP(API Received)+3 MONTHS +1 Day | 2
4 | Formulation Finalised | D4 + 3months | C5 + 1 day | 3
5 | Manufacture Pivotal batches | D5 + 1month | C6 + 7 days | 4
6 | Test and Place on Stability | D6 + 1 day | C7 + 1 month | 5
7 | Carry out Biostudy | D7 + 3 months | C8 + 2 months | 6
8 | 3 month stability Report | D7 + 4 months | c9 | 6
9 | 6 month stability Report | C9 + 3 months | c10 | 8
10 | Give last data to RA | Date from 3rd party company | C11
11 | Phase 3 Regulatory
12 | Dossier Ready Date | D11 + 1month | C13 | 10
13 | Submit DCP in interested EU countries - DCP1 | d13 + 7 days | C14 | 12
14 | RA Submission Dues Paid into Germany | D14 | D14 + 1 days | 13
15 | RA Submission Dues Paid into France | D14 | D14 + 1 days | 13
16 | RA Submission Dues Paid into Italy | D14 | D14 + 1 days | 13
17 | Submit DCP in interested EU countries - DCP2 |  |  | 10
18 | Submit DCP2 into Germany | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13
19 | Submit DCP2 into France | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13
20 | Submit DCP2 into Italy | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13
21 | Submit into Nationals
22 | Submit Nationals into UK | D13 + 28 days | C23 | 12
23 | Submit Nationals into Israel | D13 + 90 days | C24 | 12
24 | DCP Validation
25 | Validation DCP1 into Germany | D15 | C26+14 Days | 14
26 | Validation DCP1 into France | D15 | C27+14 Days | 15
27 | Validation DCP1 into Italy | D15 | C28+14 Days | 16
28 | Validation DCP2 into Germany | RA(Validation Date) | RA(Validation Date)+14 Days | 18
29 | Validation DCP2 into France | RA(Validation Date) | RA(Validation Date)+14 Days | 19
30 | Validation DCP2 into Italy | RA(Validation Date) | RA(Validation Date)+14 Days | 20
| DCP Procedure | C33 | D35
31 | DCP Starts | the latest of D29, D30, D31 + 1 day | C33 | 25, 26, 27
32 | DCP Day 105 | D33 + 105 Days | C34 | 31
33 | DCP Day 106 | D34 + file coefficient (Red, Orange, Green) | C35 | 32
34 | DCP End of Procedure (EOP) | D35 + 104 days | C36 | 33
35 | UK Validation | D23 | C37+14 Days | 22
36 | Israel Validation | D24 | C38+14 Days | 23
37 | Submit Nationals in other interested countries | D13 + |  | 12
| Pharmacovigilance requirements | D13 + 90 Days | C36 - 1 month | 12
38 | National Phase in Germany | D36 | C41 + German Coefficient | 34
39 | DCP Approval in Germany | D41 | C42 | 38
40 | National Phase in France | D36 | C43 + France Coefficient | 34
41 | DCP Approval in France | D43 | C44 | 40
42 | National Phase in Italy | D36 | C45 + Italy Coefficient | 34
43 | DCP Approval in IT | D42 | C46 | 40
44 | Approval in UK | D37 + country coefficient | C47 | 35
45 | Approval in Israel | D38 + country coefficient | C48 | 36
Phase 4 Pre Launch Preparation per country
47 | Purchase order raised UK | 12 months before D77 | C50 | 74
48 | Purchase order raised Germany | 12 months before D74 | C51 | 71
49 | Purchase order raised Italy | 12 months before D76 | C52 | 73
50 | Purchase order raised France | 12 months before D75 | C53 | 72
51 | API ordered UK | D50 + 14 days |  | 50
52 | API ordered Germany | D51 + 14 days |  | 51
53 | API ordered Italy | D52 + 14 days |  | 52
54 | API ordered France | D53 + 14 days |  | 53
55 | Cutter Guides sent to Artwork | D36 - 1 month | C58 | 34
56 | Draft Artworks completed | D58 + 25 Days | C59 | 58
57 | Artworks submitted and approved | D59 + 6 Days | C60 | 59
58 | Plan Batch manufacture | First Approval either D42, D44, D46, D47, D48 | C61 + 14 Days | 39, 41, 43, 44, 45
Phase 5 Launch Activities per country
60 | Final Artworks sent to plant | C64 - 1 month
61 | Packaging for launch stock ordered | C65 - 2 months | C64 | 62
62 | Manufacture Launch Bulk Stock | First Approval either D42, D44, D46, D47, D48 Depending on country | C61 + 14 Days | 39, 41, 43, 44, 45
63 | Approve Bulk product | C65 | D65 + 28 Days | 62
64 | Packaging for launch stock received | D64 + 60 Days |  | 61
65 | Launch Bulk packed | C65 | D65 + 21 Days | 62, 64
66 | Approve Finished product | D68 | D68 + 14 Days | 65
67 | Send product to Europe | D69 | C70 + 28 Days | 66
68 | Release product in Europe | D70 | C71 + 14 Days | 67
69 | Send product to Country | D71 | C72 + 3 Days | 68
70 | Obtain Price in Country | Approval in Country | Depends on country | 41, 43
71 | Launch in Country Germany | 4 months after approval - D42 | C74 | 39
72 | Launch in Country Italy | 4 months after approval - D44 | C75 | 41
73 | Launch in Country France | 4 months after approval - D46 | C76 | 43
74 | Launch in Country UK | 4 months after approval - D47 | C77 | 44
75 | Launch in Country Israel | 4 months after approval - D48 | C78 | 45