## Slide 1
Setup all the software on the VM
Setup GIT repository for the project
Updated the project plan with Epic & Milestone
Share the developers name onboarded for project
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Onboard architect & begin with architecture of the project
Onboard DBA & begin with database design
Setup VPN & RDP access for developers
Accomplishment for the week
Status update for the week 12th Dec 2022 to 16th Dec 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Received the VPN & RDP access from Emcure team.
Setup required software on the VM to begin with development phase.
Share updated project plan and developers name.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get sorted with pre requisite on VM/RDP to begin with development phase.
Resources
PM : 1
BA : 0
Dev : 0
Arct : 1
DBA: 1
Tester: 0
Installation of required softwares not done on the VM.

## Slide 2
Pre requisite for the development server has been installed
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Onboard developer and begin with development phase
Complete the database design for all the modules
Finalize the architecture at core level so developers can begin work
Accomplishment for the week
Status update for the week 19th Dec 2022 to 23rd Dec 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Begin with architecture & Database design of the project.
Setup VPN & RDP in developer’s system
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get sorted with RDP issues
Get sorted with GIT repo access
Get sorted with JIRA access
Resources
PM : 1
BA : 0
Dev : 0
Arct : 1
DBA: 1
Tester: 0
RDP connection is not working for more than 2 users.
Issues while using VM for development
JIRA access not provided by Emcure team

## Slide 3
Align developer’s and bein with user stories
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the architecture of the application
Accomplishment for the week
Status update for the week 26th Dec 2022 to 30th Dec 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Database design has been completed with core modules.
Core architecture has been finalized
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the GIT repository access for 1 pending developer.
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 1
Tester: 0
Delays in getting GIT repository access

## Slide 4
Architecture has been completed
Design / Theme integration has been completed
Partially completed with the PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the PIDF module.
Host the dev version of application on Emcure server
Accomplishment for the week
Status update for the week 2nd Jan 2023 to 6th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Architecture of the application has been completed.
On boarded 3rd developer on the project
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0

## Slide 5
Architecture has been completed
Design / Theme integration has been completed
Partially completed with the PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the PIDF module.
Host the dev version of application on Emcure server
Accomplishment for the week
Status update for the week 9th Jan 2023 to 13th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Architecture of the application has been completed.
On boarded 3rd developer on the project
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0

## Slide 6
Architecture has been completed
Design / Theme integration has been completed
Partially completed with the PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the PIDF module.
Host the dev version of application on Emcure server
Accomplishment for the week
Status update for the week 16th Jan 2023 to 20th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Architecture of the application has been completed.
On boarded 3rd developer on the project
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0

## Slide 7
Shared latest updated project plan with Emcure team
Finalizing PIDF & IPD module
Completed Auth implementation
Completed Audit logging integration in PIDF module.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the Epic 1 and schedule meeting for demo of portal.
On board html designer to provide support over UI
As Emcure team mentioned about delivery, planning to on board another resource.
Accomplishment for the week
Status update for the week 23rd Jan 2023 to 27th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Finalizing the core modules (Masters, Auth, PIDF & IPD) for portal.
Begin with further flow modules (PBF, Commercial & Medical)
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Host the dev vsersion of application
Finalize all the modules for Epic 1
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0