## Slide 1
Setup all the software on the VM
Setup GIT repository for the project
Updated the project plan with Epic & Milestone
Share the developers name onboarded for project
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Onboard architect & begin with architecture of the project
Onboard DBA & begin with database design
Setup VPN & RDP access for developers
Accomplishment for the week
Status update for the week 12th Dec 2022 to 16th Dec 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Received the VPN & RDP access from Emcure team.
Setup required software on the VM to begin with development phase.
Share updated project plan and developers name.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get sorted with pre requisite on VM/RDP to begin with development phase.
Resources
PM : 1
BA : 0
Dev : 0
Arct : 1
DBA: 1
Tester: 0
Installation of required softwares not done on the VM.

## Slide 2
Pre requisite for the development server has been installed
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Onboard developer and begin with development phase
Complete the database design for all the modules
Finalize the architecture at core level so developers can begin work
Accomplishment for the week
Status update for the week 19th Dec 2022 to 23rd Dec 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Begin with architecture & Database design of the project.
Setup VPN & RDP in developer’s system
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get sorted with RDP issues
Get sorted with GIT repo access
Get sorted with JIRA access
Resources
PM : 1
BA : 0
Dev : 0
Arct : 1
DBA: 1
Tester: 0
RDP connection is not working for more than 2 users.
Issues while using VM for development
JIRA access not provided by Emcure team

## Slide 3
Align developer’s and bein with user stories
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the architecture of the application
Accomplishment for the week
Status update for the week 26th Dec 2022 to 30th Dec 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Database design has been completed with core modules.
Core architecture has been finalized
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the GIT repository access for 1 pending developer.
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 1
Tester: 0
Delays in getting GIT repository access

## Slide 4
Architecture has been completed
Design / Theme integration has been completed
Partially completed with the PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the PIDF module.
Host the dev version of application on Emcure server
Accomplishment for the week
Status update for the week 2nd Jan 2023 to 6th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Architecture of the application has been completed.
On boarded 3rd developer on the project
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0

## Slide 5
Architecture has been completed
Design / Theme integration has been completed
Partially completed with the PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the PIDF module.
Host the dev version of application on Emcure server
Accomplishment for the week
Status update for the week 9th Jan 2023 to 13th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Architecture of the application has been completed.
On boarded 3rd developer on the project
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0

## Slide 6
Architecture has been completed
Design / Theme integration has been completed
Partially completed with the PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the PIDF module.
Host the dev version of application on Emcure server
Accomplishment for the week
Status update for the week 16th Jan 2023 to 20th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Architecture of the application has been completed.
On boarded 3rd developer on the project
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0

## Slide 7
Shared latest updated project plan with Emcure team
Finalizing PIDF & IPD module
Completed Auth implementation
Completed Audit logging integration in PIDF module.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Complete the Epic 1 and schedule meeting for demo of portal.
On board html designer to provide support over UI
As Emcure team mentioned about delivery, planning to on board another resource.
Accomplishment for the week
Status update for the week 23rd Jan 2023 to 27th Jan 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Finalizing the core modules (Masters, Auth, PIDF & IPD) for portal.
Begin with further flow modules (PBF, Commercial & Medical)
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Host the dev vsersion of application
Finalize all the modules for Epic 1
Resources
PM : 1
BA : 0
Dev : 3
Arct : 1
DBA : 0
Tester: 0

## Slide 8
Completed PIDF & IPD module
Implemented role & permission for all the completed modules.
Implemented flow for PIDF module.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Get all the unique pages from designer so same ecan be utilize into application
On board new developer to finish the project before timeline.
On board tester to begin with test phase for completed modules
Once infra has been setup by Emcure team setup the dev link to go through with application.
Accomplishment for the week
Status update for the week 30th Jan 2023 to 3rd Feb 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Begin with the designer, Implemented couple of unique screens
Begin with commercial, Medical & PBF modules.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Configure application on dev server
On board new developer for the project
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 0

## Slide 9
Completed unique pages html by designer, which will be integrated into our application
Begin with tester for the application
Partially completed Commercial & Medical module.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
On board new developer to finish the project before timeline.
Testing by tester on the core modules of application
Accomplishment for the week
Status update for the week 6th Feb 2023 to 10th Feb 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Begin with tester to start with test phase of the completed modules.
Begin with commercial, Medical, Dashboard & PBF modules.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
On board new developer for the project
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 0
Get new VM for 2 more users
Get SMTP settings configured to send email to outside emcure users
Open port 82 for API’s & permission of read/write on Uploads folder

## Slide 10
Completed unique pages html by designer, which will be integrated into our application
Begin with tester for the application
Partially completed Commercial & Medical module.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
On board new developer to finish the project before timeline.
Testing by tester on the core modules of application
Accomplishment for the week
Status update for the week 13th Feb 2023 to 17th Feb 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Begin with tester to start with test phase of the completed modules.
Begin with commercial, Medical, Dashboard & PBF modules.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
On board new developer for the project
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 0
Get new VM for 2 more users
Get SMTP settings configured to send email to outside emcure users
Open port 82 for API’s & permission of read/write on Uploads folder

## Slide 11
Completed unique pages html by designer, which will be integrated into our application
Begin with tester for the application
Partially completed Commercial & Medical module.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
On board new developer to finish the project before timeline.
Testing by tester on the core modules of application
Accomplishment for the week
Status update for the week 20th Feb 2023 to 24th Feb 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Begin with tester to start with test phase of the completed modules.
Begin with commercial, Medical, Dashboard & PBF modules.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
On board new developer for the project
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 0
Get new VM for 2 more users
Get SMTP settings configured to send email to outside emcure users
Open port 82 for API’s & permission of read/write on Uploads folder

## Slide 12
Completed the flow of PIDF module for Commercial, API.
Completed the Audit log integration module.
Completed testing of core modules.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the Finance and PBF modules.
Begin with Management approval & Project module.
Accomplishment for the week
Status update for the week 27th Feb 2023 to 3rd Mar 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
HTML Design |  |  | 30-Jan-23 | 
Testing |  |  | 13-Feb-23 | 
Completed flow for the PIDF management. Finalized the modules Commercial, Medical & API.
Begin with Project Management & Notification module.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get sort out all the issues related to Infra
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 1
Get new VM access for 2 more users
Get SMTP settings configured to send email to outside emcure users
Get server to host application for dev and staging environment

## Slide 13
Completed unique pages html by designer, which will be integrated into our application
Begin with tester for the application
Partially completed Commercial & Medical module.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
On board new developer to finish the project before timeline.
Testing by tester on the core modules of application
Accomplishment for the week
Status update for the week 6th Mar 2023 to 10th Mar 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Begin with tester to start with test phase of the completed modules.
Begin with commercial, Medical, Dashboard & PBF modules.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
On board new developer for the project
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 0
Get new VM for 2 more users
Get SMTP settings configured to send email to outside emcure users
Open port 82 for API’s & permission of read/write on Uploads folder

## Slide 14
Published the latest source code on new dev server provided by Emcure team
Finalized the core flow of PIDF module with all the sub modules.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Schedule meeting with Emcure team to discuss about the current implementation of module.
Get the testing done for all the modules from tester
Finalize the PBF, Finance & Management approval module.
Accomplishment for the week
Status update for the week 13th Mar 2023 to 17th Mar 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Completed all the core modules & Sub modules of PIDF
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Understand the calculation for PBF, Finance & Management approval.
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 0
VM access for new user has not been provided yet
VM was down for couple of times in past 2-3 weeks.
Get SMTP settings configured to send email to outside emcure users

## Slide 15
Finalized the core flow of PIDF module with all the sub modules.
Completed testing for core modules with data transmission
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the calculation for PBF & Finance module.
Get the testing done for all the modules with data calculation from tester
Finalize changes for integration of Project Gantt chart
Walk through of the application with Rahul to discuss about the implementation.
Accomplishment for the week
Status update for the week 20th Mar 2023 to 24th Mar 2023
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 19-Aug-22
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 | 15-Dec-22 | 6-Jan-23
Database Design | 18-Apr-22 | 22-Apr-22 | 15-Dec-22 | 30-Dec-22
Development | 25-Apr-22 | 15-Jul-22 | 26-Dec-22 | 
Finalized the flow of PIDF & Project module
Calculation section for PBF & Finance module is in progress
Testing completed for Core modules of PIDF
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Understand the calculation for Finance & Management approval module.
Resources
PM : 1
BA : 0
Dev : 3
Arct : 0
DBA : 0
Tester: 1
We were expecting to close the project by 25th March but due to couple of infra related issues (VM was down, Credentials got expired, New dev user session with VM has not been setup) its been delayed