## DeliveryPlan_20230915
Project Name | Emcure NPD (Phase 2 - Milestone 1) |  |  | Project Manager |  | YallaReddy
Start Date | 2023-07-31 | End Date |  | Overall Progress |  | 60%
Activity | Sub Activity | Epic | Start Date | End Date | Status | Progress | Remark
Phase 2 - Milestone 1 |  |  | 2023-07-19 | 2023-10-27
CR-2 | This contains all the feedback / change request, we received from Emcure team during Milestone - 1 UAT meetings. Note: There were couple of points which were minor enhancement, we have not included in this into CR-2, We have already completed and published to UAT |  | 2023-07-19 | 2023-08-04 | Completed | 100% | We need to get final signoff on CR-2 UAT changes.
Execution
CR-3 |  |  |  |  | In Progress | 40%
| P1 | Epic 1 | 2023-08-07 | 2023-08-21 | In Progress | 90% | We will finalize EPIC 1 -> PIDF, IPD, PBF - RA (Tab), PBF - General Tab, PBF - Pack Size Stability
| P1 (Note: Since we can not begin with this until PIDF & RA get finalized so its dependency on previous task) | Epic 1 | 2023-08-17 | 2023-08-28 | In Progress | 80% | We will finalize EPIC 1 -> Project Management & Master Management (workflow related to project management)
| P1 | Epic 1 | 2023-08-28 | 2023-09-04 | In Progress | 85% | Rest all items from Epic 1
| P2 | Epic 2 | 2023-09-05 | 2023-10-02 | Yet to start | 50%
Execution
CR-4 | Migration of all the Existing PIDF which is maintained in excel file right now. (P3) | Epic 3 | 2023-09-18 | 2023-10-09 | Yet to start | 0%
Execution
UAT | UAT for CR-3 & 4 |  | 2023-10-09 | 2023-10-27 | Yet to start | 0%
Phase 2 - Milestone 2 | [6 empty] | Yet to identified

## DeliveryPlan_20230908
Project Name | Emcure NPD (Phase 2 - Milestone 1) |  |  | Project Manager |  | YallaReddy
Start Date | 2023-07-31 | End Date |  | Overall Progress |  | 55%
Activity | Sub Activity | Epic | Start Date | End Date | Status | Progress | Remark
Phase 2 - Milestone 1 |  |  | 2023-07-19 | 2023-10-27
CR-2 | This contains all the feedback / change request, we received from Emcure team during Milestone - 1 UAT meetings. Note: There were couple of points which were minor enhancement, we have not included in this into CR-2, We have already completed and published to UAT |  | 2023-07-19 | 2023-08-04 | Completed | 100% | We need to get final signoff on CR-2 UAT changes.
Execution
CR-3 |  |  |  |  | In Progress | 40%
| P1 | Epic 1 | 2023-08-07 | 2023-08-21 | In Progress | 90% | We will finalize EPIC 1 -> PIDF, IPD, PBF - RA (Tab), PBF - General Tab, PBF - Pack Size Stability
| P1 (Note: Since we can not begin with this until PIDF & RA get finalized so its dependency on previous task) | Epic 1 | 2023-08-17 | 2023-08-28 | In Progress | 80% | We will finalize EPIC 1 -> Project Management & Master Management (workflow related to project management)
| P1 | Epic 1 | 2023-08-28 | 2023-09-04 | In Progress | 75% | Rest all items from Epic 1
| P2 | Epic 2 | 2023-09-05 | 2023-10-02 | Yet to start | 45%
Execution
CR-4 | Migration of all the Existing PIDF which is maintained in excel file right now. (P3) | Epic 3 | 2023-09-18 | 2023-10-09 | Yet to start | 0%
Execution
UAT | UAT for CR-3 & 4 |  | 2023-10-09 | 2023-10-27 | Yet to start | 0%
Phase 2 - Milestone 2 | [6 empty] | Yet to identified

## DeliveryPlan_20230901
Project Name | Emcure NPD (Phase 2 - Milestone 1) |  |  | Project Manager |  | YallaReddy
Start Date | 2023-07-31 | End Date |  | Overall Progress |  | 35%
Activity | Sub Activity | Epic | Start Date | End Date | Status | Progress | Remark
Phase 2 - Milestone 1 |  |  | 2023-07-19 | 2023-10-27
CR-2 | This contains all the feedback / change request, we received from Emcure team during Milestone - 1 UAT meetings. Note: There were couple of points which were minor enhancement, we have not included in this into CR-2, We have already completed and published to UAT |  | 2023-07-19 | 2023-08-04 | Completed | 100% | We need to get final signoff on CR-2 UAT changes.
Execution
CR-3 |  |  |  |  | In Progress | 40%
| P1 | Epic 1 | 2023-08-07 | 2023-08-21 | In Progress | 90% | We will finalize EPIC 1 -> PIDF, IPD, PBF - RA (Tab), PBF - General Tab, PBF - Pack Size Stability
| P1 (Note: Since we can not begin with this until PIDF & RA get finalized so its dependency on previous task) | Epic 1 | 2023-08-17 | 2023-08-28 | In Progress | 80% | We will finalize EPIC 1 -> Project Management & Master Management (workflow related to project management)
| P1 | Epic 1 | 2023-08-28 | 2023-09-04 | In Progress | 25% | Rest all items from Epic 1
| P2 | Epic 2 | 2023-09-05 | 2023-10-02 | Yet to start | 15%
Execution
CR-4 | Migration of all the Existing PIDF which is maintained in excel file right now. (P3) | Epic 3 | 2023-09-18 | 2023-10-09 | Yet to start | 0%
Execution
UAT | UAT for CR-3 & 4 |  | 2023-10-09 | 2023-10-27 | Yet to start | 0%
Phase 2 - Milestone 2 | [6 empty] | Yet to identified

## DeliveryPlan_08202023
Project Name | Emcure NPD (Phase 2 - Milestone 1) |  |  | Project Manager |  | YallaReddy
Start Date | 2023-07-19 | End Date |  | Overall Progress |  | 35%
Activity | Sub Activity | Epic | Start Date | End Date | Status | Progress | Remark
Phase 2 - Milestone 1 |  |  | 2023-07-19 | 2023-10-27
CR-2 | This contains all the feedback / change request, we received from Emcure team during Milestone - 1 UAT meetings. Note: There were couple of points which were minor enhancement, we have not included in this into CR-2, We have already completed and published to UAT |  | 2023-07-19 | 2023-08-04 | Completed | 100% | We need to get final signoff on CR-2 UAT changes.
Execution
CR-3 |  |  |  |  | In Progress | 40%
| P1 | Epic 1 | 2023-08-07 | 2023-08-21 | In Progress | 90% | We will finalize EPIC 1 -> PIDF, IPD, PBF - RA (Tab), PBF - General Tab, PBF - Pack Size Stability
| P1 (Note: Since we can not begin with this until PIDF & RA get finalized so its dependency on previous task) | Epic 1 | 2023-08-17 | 2023-08-28 | In Progress | 75% | We will finalize EPIC 1 -> Project Management & Master Management (workflow related to project management)
| P1 | Epic 1 | 2023-08-28 | 2023-09-04 | In Progress | 10% | Rest all items from Epic 1
| P2 | Epic 2 | 2023-09-05 | 2023-10-02 | Yet to start | 15%
Execution
CR-4 | Migration of all the Existing PIDF which is maintained in excel file right now. (P3) | Epic 3 | 2023-09-18 | 2023-10-09 | Yet to start | 0%
Execution
UAT | UAT for CR-3 & 4 |  | 2023-10-09 | 2023-10-27 | Yet to start | 0%
Phase 2 - Milestone 2 | [6 empty] | Yet to identified

## DeliveryPlan
Project Name | Emcure NPD (Phase 2 - Milestone 1) |  |  | Project Manager |  | Nilesh Jain
Start Date | 2023-07-19 | End Date |  | Overall Progress |  | 20%
Activity | Sub Activity | Epic | Start Date | End Date | Status | Progress | Remark
Phase 2 - Milestone 1 |  |  | 2023-07-19 | 2023-10-27
CR-2 | This contains all the feedback / change request, we received from Emcure team during Milestone - 1 UAT meetings. Note: There were couple of points which were minor enhancement, we have not included in this into CR-2, We have already completed and published to UAT |  | 2023-07-19 | 2023-08-04 | Completed | 100%
Execution
CR-3 |  |  |  |  | In Progress | 10%
| P1 | Epic 1 | 2023-08-07 | 2023-08-21 | In Progress | 30% | We will finalize EPIC 1 -> PIDF, IPD, PBF - RA (Tab), PBF - General Tab, PBF - Pack Size Stability
| P1 (Note: Since we can not begin with this until PIDF & RA get finalized so its dependency on previous task) | Epic 1 | 2023-08-17 | 2023-08-28 | Yet to start | 0% | We will finalize EPIC 1 -> Project Management & Master Management (workflow related to project management)
| P1 | Epic 1 | 2023-08-28 | 2023-09-04 | Yet to start | 0% | Rest all items from Epic 1
| P2 | Epic 2 | 2023-09-05 | 2023-10-02 | Yet to start | 0%
Execution
CR-4 | Migration of all the Existing PIDF which is maintained in excel file right now. (P3) | Epic 3 | 2023-09-18 | 2023-10-09 | Yet to start | 0%
Execution
UAT | UAT for CR-3 & 4 |  | 2023-10-09 | 2023-10-27 | Yet to start | 0%
Phase 2 - Milestone 2 | [6 empty] | Yet to identified