## TIL-In-house
Id | Task | Start Date | EndDate | Dependency | Tab that data comes from | Name of field(s)
1 | Development Phase |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0 | Formulation TDP | API ordered + API Received
3 | Select API suppliers | Formulation TDP(API Received)+3 MONTHS | Formulation TDP(API Received)+3 MONTHS +1 Day | 2 | Formulation TDP
4 | Formulation Finalised | D4 + 3months | C5 + 1 day | 3 | Formulation TDP | Final Formulation Approved
5 | Manufacture Pivotal batches | D5 + 1month | C6 + 7 days | 4 | R&D | Pivotal Batches Manufactured Completed
6 | Test and Place on Stability | D6 + 1 day | C7 + 1 month | 5 | R&D | D7 = Day 0
7 | Carry out Biostudy | D7 + 3 months | C8 + 2 months | 6 | Biostudy | D8 = Date Of Final Report
8 | 3 month stability Report | D7 + 4 months | C9 | 6 | R&D | D9 = 3 months
9 | 6 month stability Report | C9 + 3 months | C10 | 8 | R&D | D10 = 6 months
10 | Give last data to RA | the latest of D7 + D10 + 1 month | C11 | 7+9 | R&D | D11 = Last Data To Regulatory
11 | Regulatory Phase | D11 | D46 or D48 whichever is latest | 10
Receipt date from RnD
12 | Dossier Ready Date |  |  | 10 | RA | Country wise separate line item based on submission type
| Dossier submission date |  |  |  |  | Country wise separate line item based on submission type
34 | End of Procedure (EOP) date |  |  | 33 | RA | Country wise separate line item based on submission type
| Country approval Date |  |  |  |  | Country wise separate line item based on submission type
37 | Earliest Launch date |  |  | 12 | RA | Country wise separate line item based on submission type
Phase 4 Pre Launch Preparation per country
47 | Purchase order raised | 12 months before launch date |  | 74 | Country | Country wise separate line item based on submission type
51 | API ordered | D47 | C47 + 14 days | 50 | Operations | Country wise separate line item based on submission type
55 | Cutter Guides sent to Artwork | EOP date - 1 month | C22 | 34 | Operations | Cutter Guides sent to plant
56 | Draft Artworks completed | D22 + 25 days | C23 | 58 | Artwork | Artworks completed
57 | Artworks submitted and approved | D23+6 days | C24 | 59 | Artwork | Artworks submitted and approved
58 | Plan Batch manufacture | Country approval whichever date is earlier | C25+15 days | 39, 41, 43, 44, 45 |  | Batch manufacture
| Phase 5 Launch Activities per country |  |  |  |  | country Launch
60 | Final Artworks sent to plant |  |  |  | Artwork | Date sent to plant
61 | Packaging for launch stock ordered |  |  | 62 |  | Packaging for launch stock ordered
62 | Manufacture Launch Bulk Stock |  |  | 39, 41, 43, 44, 45 | Operations | Launch Bulk Stock Manufactured
63 | Approve Bulk product |  |  | 62 | Quality | Approve Bulk Product
64 | Packaging for launch stock received |  |  | 61 | Operations | Packaging for launch stock received
65 | Launch Bulk packed |  |  | 62, 64 | Operations | Launch Bulk packed
66 | Approve Finished product |  |  | 65 | Quality | Approve Finished product
67 | Send product to Europe |  |  | 66 | Logistics | "Plant dispatch date" to "Arrival Port in EU"
68 | Release product in Europe |  |  | 67 | Quality | Release Finished Product
69 | Send product to Country |  |  | 68 | Logistics | "Despatch Date in EU" to "Arrival in country"
70 | Obtain Price in Country |  |  | 41, 43 | Country Tabs | Country Price
71 | Launch in Country Germany | 4 months after approval |  | 39 | Germany Country | Launch date country wise separate line item

## Sheet2
RA |  | Project Manage
Field | Date | Field | Country | Start Date | End Date
Receit Date From RnD | 2023-09-01 | Dossier Ready Date | France | 2023-09-01 | 2023-11-01
Last data from R&D | 2023-09-01 | Dossier Submission Date | France | 2023-09-01 | 2023-11-01
Dossier Ready Date | 2023-11-01 | End of procedure Date | France | 2023-11-02 | 2024-05-01
Dossier Submission Date | 2023-11-01 | Country Approval Date | France | 2024-05-02 | 2024-09-01
End of procedure Date | 2024-05-01 | Earliest Launch - | France
Country Approval Date | 2024-09-01 | Dossier Ready Date | Italy
Earliest Launch - | 2025-01-01 | Dossier Submission Date | Italy
|  | End of procedure Date | Italy
|  | Country Approval Date | Italy
|  | Earliest Launch - | Italy
Formulas:
Start Date = [Date]
Start Date = [Date, row below]+1

## Global
Id | Task | Start Date | EndDate | Dependency | Tab that data comes from | Name of field(s)
1 | Development Phase |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0 | Formulation TDP | API ordered + API Received
3 | Select API suppliers | Formulation TDP(API Received)+3 MONTHS | Formulation TDP(API Received)+3 MONTHS +1 Day | 2 | Formulation TDP
4 | Formulation Finalised | D4 + 3months | C5 + 1 day | 3 | Formulation TDP | Final Formulation Approved
5 | Manufacture Pivotal batches | D5 + 1month | C6 + 7 days | 4 | R&D | Pivotal Batches Manufactured Completed
6 | Test and Place on Stability | D6 + 1 day | C7 + 1 month | 5 | R&D | D7 = Day 0
7 | Carry out Biostudy | D7 + 3 months | C8 + 2 months | 6 | Biostudy | D8 = Date Of Final Report
8 | 3 month stability Report | D7 + 4 months | C9 | 6 | R&D | D9 = 3 months
9 | 6 month stability Report | C9 + 3 months | C10 | 8 | R&D | D10 = 6 months
10 | Give last data to RA | the latest of D7 + D10 + 1 month | C11 | 7+9 | R&D | D11 = Last Date To Regulatory
11 | Regulatory Phase | D11 | D46 or D48 whichever is latest | 10
12 | Dossier Ready Date |  |  | 10 | RA | Dossier Ready Date
13 | Submit Dossier in interested countries |  |  | 10 | RA
14 | Submit Dossier into Germany |  |  | 13 | RA | Submission Dues Paid
15 | Submit Dossier into France |  |  | 13 | RA | Submission Dues Paid
16 | Submit Dossier into Italy |  |  | 13 | RA | Submission Dues Paid
17 | Dossier Approval in Germany |  |  | 38 | RA | Germany Approval
18 | Dossier Approval in France |  |  | 34 | RA | France Phase
19 | Dossier Approval in Italy |  |  | 40 | RA | France Approval
20 | Phase 4 Pre Launch Preparation per country
21 | Purchase order raised UK |  |  | 74 | Country | UK
22 | Purchase order raised Germany |  |  | 71 | Country | Germany
23 | Purchase order raised Italy |  |  | 73 | Country | Italy
24 | Purchase order raised France |  |  | 72 | Country | France
25 | Artworks submitted and approved |  |  | 59 | Artwork | Artworks submitted and approved
26 | Plan Batch manufacture |  |  | 39, 41, 43, 44, 45 |  | Batch manufacture
27 | Phase 5 Launch Activities per country |  |  |  |  | country Launch
28 | Final Artworks sent to plant |  |  |  | Artwork | Date sent to plant
29 | Send product to country |  |  | 66 | Logistics | "Plant dispatch date" to "Arrival Port in EU"
30 | Release product in Country |  |  | 67 | Quality | Release Finished Product
31 | Send product to Country |  |  | 68 | Logistics | "Despatch Date in EU" to "Arrival in country"
32 | Obtain Price in Country |  |  | 41, 43 | Country Tabs | Country Price
33 | Launch in Country |  |  | 39 | Germany Country | Launch date

## Third PArty
Id | Task | Start Date | EndDate | Dependency | Tab that data comes from | Name of field(s)
1 | Development Phase |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0 | Formulation TDP | API ordered + API Received
3 | Select API suppliers | Formulation TDP(API Received)+3 MONTHS | Formulation TDP(API Received)+3 MONTHS +1 Day | 2 | Formulation TDP
4 | Formulation Finalised | D4 + 3months | C5 + 1 day | 3 | Formulation TDP | Final Formulation Approved
5 | Manufacture Pivotal batches | D5 + 1month | C6 + 7 days | 4 | R&D | Pivotal Batches Manufactured Completed
6 | Test and Place on Stability | D6 + 1 day | C7 + 1 month | 5 | R&D | D7 = Day 0
7 | Carry out Biostudy | D7 + 3 months | C8 + 2 months | 6 | Biostudy | D8 = Date Of Final Report
8 | 3 month stability Report | D7 + 4 months | C9 | 6 | R&D | D9 = 3 months
9 | 6 month stability Report | C9 + 3 months | C10 | 8 | R&D | D10 = 6 months
10 | Give last data to RA | the latest of D7 + D10 + 1 month | C11 | 7+9 | R&D | D11 = Last Data To Regulatory
11 | Regulatory Phase | D11 | D46 or D48 whichever is latest | 10
Receipt date from RnD
12 | Dossier Ready Date |  |  | 10 | RA | Country wise separate line item based on submission type
| Dossier submission date |  |  |  |  | Country wise separate line item based on submission type
34 | End of Procedure (EOP) date |  |  | 33 | RA | Country wise separate line item based on submission type
| Country approval Date |  |  |  |  | Country wise separate line item based on submission type
37 | Earliest Launch date |  |  | 12 | RA | Country wise separate line item based on submission type
Phase 4 Pre Launch Preparation per country
47 | Purchase order raised | 12 months before launch date |  | 74 | Country | Country wise separate line item based on submission type
51 | API ordered | D47 | C47 + 14 days | 50 | Operations | Country wise separate line item based on submission type
55 | Cutter Guides sent to Artwork | EOP date - 1 month | C22 | 34 | Operations | Cutter Guides sent to plant
56 | Draft Artworks completed | D22 + 25 days | C23 | 58 | Artwork | Artworks completed
57 | Artworks submitted and approved | D23+6 days | C24 | 59 | Artwork | Artworks submitted and approved
58 | Plan Batch manufacture | Country approval whichever date is earlier | C25+15 days | 39, 41, 43, 44, 45 |  | Batch manufacture
| Phase 5 Launch Activities per country |  |  |  |  | country Launch
60 | Final Artworks sent to plant |  |  |  | Artwork | Date sent to plant
61 | Packaging for launch stock ordered |  |  | 62 |  | Packaging for launch stock ordered
62 | Manufacture Launch Bulk Stock |  |  | 39, 41, 43, 44, 45 | Operations | Launch Bulk Stock Manufactured
63 | Approve Bulk product |  |  | 62 | Quality | Approve Bulk Product
64 | Packaging for launch stock received |  |  | 61 | Operations | Packaging for launch stock received
65 | Launch Bulk packed |  |  | 62, 64 | Operations | Launch Bulk packed
66 | Approve Finished product |  |  | 65 | Quality | Approve Finished product
67 | Send product to Europe |  |  | 66 | Logistics | "Plant dispatch date" to "Arrival Port in EU"
68 | Release product in Europe |  |  | 67 | Quality | Release Finished Product
69 | Send product to Country |  |  | 68 | Logistics | "Despatch Date in EU" to "Arrival in country"
70 | Obtain Price in Country |  |  | 41, 43 | Country Tabs | Country Price
71 | Launch in Country Germany | 4 months after approval |  | 39 | Germany Country | Launch date country wise separate line item