## Sheet1
Modules | SubModule | Description | Emcure Contact Person | Assigned To | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | RG Status | Wireframe Status | SRS Status | Signoff | Notes/ Comments
Project Kickoff Meeting |  |  |  | Saumil | 2022-02-03 | 2022-02-03 |  |  | Pending
Stakeholder Introduction |  |  |  |  | 2022-02-03 | 2022-02-03 |  |  | Pending
Setting Up Communication Channel - Everyday standup call |  |  |  | Khevna | 2022-02-03 | 2022-02-03 |  |  | Pending
Theme Finalization before the wireframe starts
Admin Panel | Login/Logout | [7 empty] | Pending | Pending | Pending | Pending
| Dashboard | [7 empty] | Pending | Pending | Pending | Pending
Forgot password
| Roles | o Internal User o Department User o Finance User o R&D o Management o Administrator
User Management
| Master Management | o User Master o Project Template Master o Formula Master o Task Master o NPD Type master o API Master o Product/molecule Master
NPD List
PIDF List
Projects | Add/edit/delete proj
Project Listing
Project Details
Project Task
Gantt Chart
Artwork | Upload /Download Dossier
Dossier Listing
Dossier Management | Edit Dossier
Archive Dossier
Dossier Versioning
Task Master | NPD
API
Tech Transfer
Add/edit/delete task
Task List
Task Details
User Module | * Login /Logout
Dashboard
* Forgot password
Create New Product Development Request
Request Approval Process
* NPD List
PIDF Forms | Market Forecast
Cost of goods and services
IP-expected litigation cost
Regulatory filings
Medical Clinical Trials
Biological Studies
SCM - Freight Cost
Manufacturing - API Cost
Manufacturing - Raw material
PIDF Approval Process
* PIDF List
* Project Listing
* Project Details
* Project Task
* Gantt Chart
Email Notification | Project Creation
Task Updates
Nearing Due Date
Artwork | * Upload /Download Dossier
* Dossier Listing
Dossier Management | * Edit Dossier
* Archive Dossier
* Dossier Versioning
Department User Module | * Login/ Logout
* Forgot password
* NPD List
* PIDF List
* PIDF Forms
Finance User Module | * Login/ Logout
* Forgot password
Dashboard
* NPD List
* PIDF List
Review PIDF - Finance Details
PIDF Approval Process
RnD User Module | * Login/ Logout
* Forgot password
Dashboard
* Create New Product Development Request
* NPD List
* PIDF List
Projects | * Add/edit/delete proj
* Project Listing
* Project Details
* Project Task
* Gantt Chart
Artwork | * Upload /Download Dossier
* Dossier Listing
Dossier Management | * Edit Dossier
* Archive Dossier
* Dossier Versioning
Management User Module | * Login/ Logout
* Forgot password
Dashboard
* NPD List
* PIDF List
PIDF Approval Process
Projects | * Add/edit/delete proj
* Project Listing
* Project Details
* Project Task
* Gantt Chart
Artwork | * Upload /Download Dossier
* Dossier Listing
Dossier Management | * Edit Dossier
* Archive Dossier
* Dossier Versioning