## Sheet1
Information | Frequency | Responsibility | Audience | Medium | Comment / Remark
Status Meetings | Weekly | PM | Key Stakeholders ( Emcure and NeoSOFT) | Teams | Planned to conduct every Friday between 12 to 12. 30 PM IST from 11-March-2022
Steering Committee Meeting | upon each Milestone or as and when required | PM | Key Stakeholders, Steering Committee | Email, Phone/ Teams/Skype
Approvals | As and when required | Emcure PM | Emcure stake holders | Emails
Sprint review Meetings | Biweekly (Every 2 Weeks) | PM | Key Stakeholders ( Emcure and NeoSOFT) | Phone/Teams/Skype | This will begin after every sprint of development phase.
Standup Meeting* | Every day (Till the discovery phase is completed) | Emcure + NeoSOFT (PM/ BA) | Key Stakeholders ( Emcure and NeoSOFT) | Phone/Teams/Skype
Note: During the requirement gathering phase, we need the availability of all the key stakeholders from each department atleast of couple of hours everyday.