## CR_Summary
Sr. No. | CR Number | CR Title | Backend | Testing | UAT | Design | BA | PM | Total Hours
1 | CR1 | Changing architecture from monolithik MVC to Service oriented architecture (SOA) | 260 | 0 | 0 | 0 | 0 | 0 | 260
2 | CR2 | Number of master forms have been increased | 100 | 20 | 15 | 0 | 40 | 25 | 200
3 | CR3 | PIDF, PBF, IPD Module Complexity | 160 | 35 | 30 | 25 | 50 | 30 | 330
4 | CR4 | Log History / Audit Trail for PIDF module | 100 | 20 | 10 | 5 | 15 | 10 | 160
|  | Total Hours | 620 | 75 | 55 | 30 | 105 | 65 | 950

## CR1
Project Name | Emcure NPD | Change Number | 01
Change Requested By | Vikas Tripathi / Narendra Upasani | Change Impact | Very high
Change title | Changing architecture from monolithik MVC to Service oriented architecture (SOA)
Change description | As per discssion over Microsoft teams, Emcure stakeholders had confirmed that for this project we will go with service oriented architecture, since in the future they are having plan to build mobile application for same project. Infrastructure for this project will be on premises IIS server.
Initial proposal | As per scope / proposal (3.2 - Technology/Environment Specifications "Page No: 11") we have estimated this application with Monolithik Core MVC application.
Change reason | Client's request
Action taken | NeoSOFT team have prepared spreadsheet with difference between SOA, Monolithik & Microservices. NeoSOFT team have prepared new architecture diagram & shared with Emcure stakeholders. Emcure team have provided approval over architecture diagram and confirmation to go with SOA architecture.
Area of change | Backend |  |  | Total Hours
Effort estimation | 260 |  |  | 260
Note | This impact will be on complete project, Here I have added this CR estimate for only those module whose requirement gathering is done. SOA CR will be added separate for modules (Artwork & Dossier) which yet to identify in requirement gathering phase.
Effecting work | 1. API application architecture & common utilites (swagger, response status, time out, error handling etc..) 2. Prepared sheet with difference between architecture (shared last week of April) 3. Prepared new SOA based architecture diagram 4. Every action throughout scope will need to go through API methods, so additional effort will be there to implement action methods and handle data transmission/timeout/request/response/error etc..

## CR2
Project Name | Emcure NPD |  | Change Number | 02
Change Requested By | Rahul Patil / SID |  | Change Impact | High
Change title | Number of master forms have been increased
Change description | We will have different masters to support PIDF module.
Initial proposal | As per scope / proposal (3.5.6 - Master Management "Page No: 15") we have assumed (upto 8-10) masters, Now after requirement gathering phase we are having 25-30 masters
Change reason | Client's request
Action taken | We have identified more masters in requirement gathering phase & same has been added into wireframe and SRS. Wireframe: https://ahqi5f.axshare.com/
Area of change | Backend | Testing | UAT | Design | BA | PM | Total Hours
Effort estimation | 100 | 20 | 15 | 0 | 40 | 25 | 200
Note | Here we are estimating for upto 30 masters, later if we will have more masters than need to estimate those separately.
Effecting work | 1. Development (CRUD Operation) of upto 30 master forms 2. Database schemas for master forms 3. Testing efforts to test identified masters 4. UAT efforts 5. BA efforts to incorporate into SRS and Wireframe 6. PM efforts

## CR3
Project Name | Emcure NPD |  | Change Number | 03
Change Requested By | Rahul Patil / SID |  | Change Impact | Very high
Change title | PIDF, PBF, IPD Module Complexity
Change description | PIDF module comes up with more new screen / complexity than mentioned in scope / proposal
Initial proposal | As per scope / proposal we have estimated this with having 5-6 sub forms (Having around 7-10 fields) (3.11 - Work Breakdown Structure "Page : 36") & now it get increased to around 12+ sub forms with having multiple fields (some places we are having around 30+ fields) & calculations. We have identified some new screens aswell beging charter summary in it.
Change reason | Client's request
Action taken | We have identified more sub forms, screens & formulas in it & same has been added into wireframe and SRS. Wireframe: https://ahqi5f.axshare.com/
Area of change | Backend | Testing | UAT | Design | BA | PM | Total Hours
Effort estimation | 160 | 35 | 30 | 25 | 50 | 30 | 330
Note
Effecting work | 1. Development effort due to new charter summary & complexity of PIDF module 2. HTML Efforts will be required to prepare UI of accordion / tabs / tables. 3. Testing efforts to test identified masters 4. UAT efforts 5. BA efforts to incorporate into SRS and Wireframe 6. PM efforts

## CR4
Project Name | Emcure NPD |  | Change Number | 04
Change Requested By | Rahul Patil / SID |  | Change Impact | High
Change title | Log History / Audit Trail for PIDF module
Change description | Need to maintain history/Audit Trail of complete PIDF form, where any updation happen with change in field values. This should managed through out PIDF, PBF, IPD, Commercial process
Initial proposal | As per scope / proposal (3.8.7 - PIDF approval "Page: 25"), We have considered Audit trail for rejection and comment in NPD and PIDF.
Change reason | Client's request
Action taken | We have identified this in requirement gathering phase & same has been added into wireframe and SRS. Wireframe: https://ahqi5f.axshare.com/
Area of change | Backend | Testing | UAT | Design | BA | PM | Total Hours
Effort estimation | 100 | 20 | 10 | 5 | 15 | 10 | 160
Note | Here we will maintain log history for complete PIDF module / process (PIDF, PBF, IPD etc..). We need to build generic solution for PIDF module to identify any value change in any field.
Effecting work | 1. Development efforts due to audit trail to manage through out PIDF module 2. Testing efforts to test identified masters 3. UAT efforts 4. BA efforts to incorporate into SRS and Wireframe 5. PM efforts