## DeliveryPlan
Project Name | Emcure NPD |  |  |  | Project Manager |  |  | Nilesh Jain
Start Date | 2022-09-05 | End Date |  |  | Overall Progress |  |  | 0%
Activity | Sub Activity |  | Epic | Start Date | End Date | Status | Assigned To | Progress | Remark
Milestone 1 | R&D and Procurement Modules |  |  | 2022-09-05 | 2022-12-16 |  |  |  | End date mentioned is including UAT
| Database |  | Epic 1 | 2022-09-05 | 2022-09-16 | Yet to start | DBA | 0%
| Architecture |  | Epic 1 | 2022-09-05 | 2022-09-30 | Yet to start | SA | 0%
| Design Integration |  | Epic 1 | 2022-09-12 | 2022-09-16 | Yet to start | Developer 1 | 0%
| Administration |  | Epic 2 |  |  | Yet to start | Developer 1 | 0%
|  | Login/Logout |  | 2022-09-12 | 2022-10-14 | Yet to start | Developer 1 | 0%
|  | Forgot password |  | 2022-10-17 | 2022-10-21 | Yet to start | Developer 1 | 0%
|  | Change Password |  | 2022-10-17 | 2022-10-21 | Yet to start | Developer 1 | 0%
| User Management | Create/Edit/Delete & Auth | Epic 2 | 2022-10-03 | 2022-10-14 | Yet to start | Developer 1 | 0%
| Roles Management | Create/Edit/Delete & Permission | Epic 1 | 2022-09-19 | 2022-09-30 | Yet to start | Developer 1 | 0%
| Dashboard |  | Epic 3 | 2022-11-28 | 2022-12-02 | Yet to start | Developer 1 | 0%
| Master Management |  | Epic 3 | 2022-10-24 | 2022-11-25 | Yet to start | Developer 1 | 0% | We are having around 25-30 forms
| PIDF |  | Epic 1 | 2022-09-12 | 2022-09-23 | Yet to start | Developer 3 | 0% | All its sub module will be taken care by assigned developer
|  | Listing |  |  |  | Yet to start |  | 0%
|  | Create / Form |  |  |  | Yet to start |  | 0%
| IPD |  | Epic 1 | 2022-09-19 | 2022-09-30 | Yet to start | Developer 3 | 0% | All its sub module will be taken care by assigned developer
|  | List |  |  |  | Yet to start |  | 0%
|  | Create / Form |  |  |  | Yet to start |  | 0%
| PBF |  | Epic 2 | 2022-09-12 | 2022-10-07 | Yet to start | Developer 2 | 0% | All its sub module will be taken care by assigned developer
|  | RnD |  |  |  | Yet to start |  | 0%
|  | Analytical |  |  |  | Yet to start |  | 0%
|  | Clinical |  |  |  | Yet to start |  | 0%
|  | Packaging |  |  |  | Yet to start |  | 0%
| API |  | Epic 2 | 2022-10-10 | 2022-11-04 | Yet to start | Developer 2 | 0% | All its sub module will be taken care by assigned developer
|  | List |  |  |  | Yet to start |  | 0%
|  | IPD |  |  |  | Yet to start |  | 0%
|  | RnD |  |  |  | Yet to start |  | 0%
|  | Charter |  |  |  | Yet to start |  | 0%
|  | Charter Summary |  |  |  | Yet to start |  | 0%
| Medical |  | Epic 2 | 2022-10-03 | 2022-10-14 | Yet to start | Developer 3 | 0%
| Commercial |  | Epic 2 | 2022-10-17 | 2022-10-21 | Yet to start | Developer 3 | 0%
| Finance |  | Epic 2 | 2022-10-24 | 2022-11-04 | Yet to start | Developer 3 | 0%
| Management Approval |  | Epic 3 | 2022-11-07 | 2022-11-11 | Yet to start | Developer 3 | 0%
| Log History / Details |  | Epic 3 | 2022-11-14 | 2022-12-02 | Yet to start | Developer 3
| Project |  | Epic 3 | 2022-11-07 | 2022-12-02 | Yet to start | Developer 2 | 0% | All its sub module will be taken care by assigned developer
|  | Add/edit/delete project |  |  |  | Yet to start |  | 0%
|  | Project Listing |  |  |  | Yet to start |  | 0%
|  | Project Details |  |  |  | Yet to start |  | 0%
|  | Project Task |  |  |  | Yet to start |  | 0%
|  | Gantt Chart |  |  |  | Yet to start |  | 0%
| QA TESTING (Functional) |  |  |  |  | Yet to start |  | 0%
|  | Test Execution | Epic 3 | 2022-11-07 | 2022-12-16 | Yet to start | Tester | 0%
|  | Testing Rework | Epic 3 | 2022-11-28 | 2022-12-16 | Yet to start |  | 0%
| UAT |  | Epic 3 | 2022-11-28 | 2022-12-16 | Yet to start |  | 0%
Execution
Milestone 2 | Artwork Module
ArtWork
Dossier
Dossier Listing
Edit Dossier
Archive Dossier
Dossier Versioning
Upload /Download Dossier
QA TESTING (Functional)
Test Execution
Testing Rework
UAT
Execution
Milestone 3 | Multi-tenant Architecture
Execution
Milestone 4 | Final UAT
System Integration Testing
Testing Execution
Testing Rework
Final Deployment (UAT)
Final Release
Packaging & building activites
User Manual Preparation
Pre Release Review by SQA
End User Training

## Epics
Sr. No. | Title | Start Date | End Date | Remark
Milestone 1 - R&D and Procurement Modules
1 | Epic 1 | 2022-09-05 | 2022-09-30
2 | Epic 2 | 2022-09-12 | 2022-11-04
3 | Epic 3 | 2022-11-07 | 2022-12-16
Milestone 2 - Artwork Module
Milestone 3 - Multi-tenant Architecture
Milestone 4 - Final UAT