## Requirement_Gather_SignOff
Sr. No. | Modules | Sub Modules | % Weitage | Requirement Done |  | Signed-Off
1 | Login |  | 4 | 1 | 4 | 1 | 4
2 |  | Login/Logout |  |  | 0 |  | 0 | 1. These all are ball-park weightage as per current understanding & houes estimation of modules. 2. 0.75 in requirement gathering are given to those modules on which the req may affect as per current changes or upcoming requirements. 3. All the sub modules is not defined in this sheet, we have covered all main modules and give weightage accordingly.
3 |  | Forgot password |  |  | 0 |  | 0
4 |  | Change Password |  |  |  |  | 0
5 | User Management |  | 3 | 1 |  | 1 | 3
6 |  | Create/Edit/Delete |  |  |  |  | 0
7 | Roles Management |  | 5 | 1 | 5 | 1 | 5
8 |  | Role Creation and Permissons |  |  | 0 |  | 0
9 | Dashboard |  | 5 | 0.75 | 3.75 | 1 | 5
10 | Master Management |  | 10 | 0.8 | 8 | 1 | 10
11 |  | Formulation |  |  | 0 |  | 0
12 | PIDF |  | 18 | 1 | 18 | 1 | 18
13 |  | PIDF Listing |  |  |  |  | 0
14 |  | Commercial Details |  |  | 0 |  | 0
15 | PBF |  | 15 | 1 | 15 | 1 | 15
16 |  | RnD |  |  | 0 |  | 0
17 |  | Analytical |  |  | 0 |  | 0
18 |  | Clinical |  |  | 0 |  | 0
19 |  | Project Charter |  |  | 0 |  | 0
20 |  | API R&D |  |  |  |  | 0
21 | IPD |  | 5 | 1 | 5 | 1 | 5
22 | Finance/COGS |  | 5 | 1 | 5 | 1 | 5
23 | Management Approval |  | 3 | 0.6 | 1.8 | 1 | 3
24 | Project |  | 10 | 0.4 | 4 | 1 | 10
25 |  | Add/edit/delete proj |  |  | 0 |  | 0
26 |  | Project Listing |  |  | 0 |  | 0
27 |  | Project Details |  |  | 0 |  | 0
28 |  | Project Task |  |  | 0 |  | 0
29 |  | Gantt Chart |  |  | 0 |  | 0
30 | ArtWork |  | 7 | 0 | 0 | 0 | 0
31 |  |  |  |  | 0 |  | 0
32 | Dossier |  | 10 | 0 | 0 | 0 | 0
33 |  | Dossier Listing |  |  | 0 |  | 0
34 |  | Edit Dossier |  |  | 0 |  | 0
35 |  | Archive Dossier |  |  | 0 |  | 0
36 |  | Dossier Versioning |  |  | 0 |  | 0
37 |  | Upload /Download Dossier |  |  | 0 |  | 0
38 | Total Weightage |  | 100 | 69.55 |  | 83
|  |  | Total % Scope of work | Total % of work completed with requirement gathering phase |  | Total % of work signed off from Emcure team
|  |  | Ball park work signed off in weeks for 1 developer |  |  | 20.2889