## Sheet1
Sr. No | Modules | Remark / Comment | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Notes/ Comments
1 | Received Source Code |  | 2022-03-09 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Complete
2 | Database mismatch & Setup working version in local system |  | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-15 | Complete
3 | Setup source code in local system and NeoSOFT environment |  | 2022-03-14 | 2022-03-16 | 2022-03-14 |  | In Progress
4 | Analyze source code by PM & SA team |  | 2022-03-16 | 2022-03-22 | 2022-03-15 |  | In Progress
5 | Identify modules available and can be utilize / customization required |  | 2022-03-22 | 2022-03-22 |  |  | Yet to start
6 | Analyze with BA & PM to identify modules as per scope |  | 2022-03-22 | 2022-03-23 |  |  | Yet to start
7 | Prepare report with analysis |  | 2022-03-23 | 2022-03-23 |  |  | Yet to start
8 | Present report in weekly status call |  | 2022-03-25 | 2022-03-25 |  |  | Yet to start