## Slide 1
Completed the following
  Prepared the wireframe for common, PIDF & PBF modules
  Prepared SRS document and shared with Emcure team to get signoff
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the baselline requirement with proposal to create CR report
Once we will receive signoff over shared SRS begin with development
Base line the pending modules requirmeent
Accomplishment for the week
Status update for the week 4th Apr 2022 to 8th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Baseline the requirment for common modules, PIDF & PBF.
SRS and Wireframe has been prepared and shared with Emcure team to get signoff
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 54
Effort burnt till date : 210
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
More changes are happening with wireframe / SRS & Delays in baseline requirement
Delays in getting signoff over SRS

## Slide 2
Completed the following
  Integrated CR for PIDF & PBF module.
  Updated SRS document and shared with Emcure team to get signoff
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Get sign-off on the SRS & Wireframe shared
Begin with development, once we will have base details.
Base line the pending modules requirmeent
Accomplishment for the week
Status update for the week 11th Apr 2022 to 15th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
SRS and Wireframe has been prepared and shared with Emcure team to get signoff
Share details required before begin with development phase.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 50
Effort burnt till date : 260
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
More changes are happening with wireframe / SRS & Delays in baseline requirement
Delays in getting signoff over SRS
Delays in complete the requirement gathering phase

## Slide 3
Completed the following
  Integrated CR for PIDF & PBF module.
  Updated SRS document and shared with Emcure team to get signoff
  Received Verbal sign off from the Emcure team (SID).
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Get clear sign-off email from Emcure team.
Begin with solution architect, once we will have base details.
Base line the pending modules requirment
Clear out all the technical details for this project.
Accomplishment for the week
Status update for the week 18th Apr 2022 to 22th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Updated SRS, Wireframe has been prepared, shared with Emcure team to get sign-off
Share details required before begin with development phase.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 27
Effort burnt till date : 287
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Technical details are not finalized, Delay while getting base details to begin with development
Delays in getting signoff over SRS
Delays in complete the requirement gathering phase

## Slide 4
Completed the following
  Different architecture option document
  Received sign-off from few stakeholder
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the technical approach
Begin with solution architect, once we will have base details.
Base line the pending modules requirment
Clear out all the technical details
Accomplishment for the week
Status update for the week 25th Apr 2022 to 29th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Prepare consolidated document with different approach to begin with development
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 23
Effort burnt till date : 310
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Technical details are not finalized
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase