## Slide 1
Completed the following
  Integrated changes in PIDF module
  Sign-off over partial modules
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Discuss about modules which has been signed off with current scope
Accomplishment for the week
Status update for the week 1st August 2022 to 5th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Received high level sign-off from Emcure team on SRS & wireframe shared
Integrated minor changes in wireframe with screens and linking
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 16
Effort burnt till date : 507
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in complete the requirement gathering phase

## Slide 2
Completed the following
  CR Report
  Identify signed - off modules
  Scheduled meeting with Emcure stakeholder to discuss about key pointers before begin with development
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Discuss about key pointers before begin with development phase
Discuss about CR, Commercial & mile stone
Accomplishment for the week
Status update for the week 8th August 2022 to 12th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Identify all the modules which has been signed off
Prepare role metrix for PIDF module
Prepare CR report as per signed off scope
Discuss about development infra and commercial
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 19
Effort burnt till date : 526
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0

## Slide 3
Completed the following
  Integrate changes in dashboard module.
  Integrate minor changes into SRS & wireframe
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the project planning document
Confirmation over commercial milestone & development infrastructure
Accomplishment for the week
Status update for the week 15th August 2022 to 19th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Begin with preparing project planning for development phase
Commercial and mile stone.
Development Infrastructure
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 2
Effort burnt till date : 528
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Commercial milestone
Development infrastructure

## Slide 4
Completed the following
  Project Planning document
  CR Report
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Close the pre development pointers
Accomplishment for the week
Status update for the week 22nd August 2022 to 26th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Updated project planning document and marked with V1.
Updated CR report with V4 version.
Finalized the Commercial and development milestone.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 15
Effort burnt till date : 543
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0