## Slide 1
Completed the following
  Integrated changes in PIDF module
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 4th July 2022 to 8th July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 5
Effort burnt till date : 477.5
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 2
Completed the following
  Integrated changes in PIDF module
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 11th July 2022 to 15th July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 8.5
Effort burnt till date : 486
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 3
Completed the following
  Integrated changes in PIDF module
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 18th July 2022 to 22nd July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 0
Effort burnt till date : 486
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 4
Completed the following
  Integrated changes in PIDF module
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 25th July 2022 to 29th July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 5
Effort burnt till date : 491
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase