## Slide 1
Nilesh Jain assigned as the Project Manager and Khevna identified as the senior business analyst
Completed the following
  Kick-off presentation
  Requirements gathering plan
Internal review conducted on 2nd Mar 2022
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Project Kick-off
To share the Requirements plan to the client and identify the relevant stakeholders from Emcure
To commence the requirements gathering phase
Accomplishment for the week
Status update for the week 28th Feb 2022 to 4th Mar 2022
Phase | MIS Start date | MIS End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 |  | 
Req. gathering | 7-Mar-22 |  |  | 
Project kick-off planed for 7th March 2022
Requirements gathering phase to follow for 6 weeks
Will adapt hybrid development model
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 20
Effort burnt till date : 20
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in approvals
Scope creep
Delays in scheduling the meeting with Emcure stakeholders

## Slide 2
Rachit Goyal identified as secondary business analyst
Completed the following
  Kick-off presentation
  Requirements gathering plan
  High level understanding about the application
  Identification of system masters
  Flow diagram
  Department wise form input mapping
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the source code & database for utilize in new application
Identify modules to be utilize from the existing application
Requirement Gathering for modules
Accomplishment for the week
Status update for the week 7th Mar 2022 to 11th Mar 2022
Phase | MIS Start date | MIS End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Project kick-off happened on 7th March 2022
Begin with requirement gathering phase
Received existing application source code & database for analysis
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 33.5
Effort burnt till date : 53.5
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings

## Slide 3
Completed the following
  Set up existing application in NeoSOFT environment
  Created communication & code analysis plan
  Flow diagram
  Department wise form input mapping
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the source code & database
Identify modules to be utilize from the existing application
Requirement Gathering for modules
Creating wireframes
Prepare code analysis report
Accomplishment for the week
Status update for the week 14th Mar 2022 to 18th Mar 2022
Phase | MIS Start date | MIS End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 
Created work flow, data transmission between department
Begin with creating wireframe of modules
Begin with code analysis for utilize into new app
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 40.5
Effort burnt till date : 94
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings

## Slide 4
Completed the following
  Flow diagram finalization
  Created wireframe for PIDF & PBF
  Created wireframe for masters
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the complete source code & database
Prepare report of code analysis & reutilization
Requirement Gathering for modules
Creating wireframes
Begin with writing SRS document
Accomplishment for the week
Status update for the week 21st Mar 2022 to 25th Mar 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 
Created wireframe for masters & PIDF form
Gone through with every screen, source code & database schemas
Understanding about mapping between PIDF & PBF
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 32
Effort burnt till date : 126
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings

## Slide 5
Completed the following
  Code analysis report
  PIDF & PBF flow
  Wireframe for 60% modules.
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Requirement Gathering for Dossier, Project & Artwork module
Creating wireframes & SRS document
Base line all the requirement and prepare document for signoff
Analyze the CR for baslined modules
Accomplishment for the week
Status update for the week 28th Mar 2022 to 1st Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Baseline the requiredment for 60% modules
Code Analysis has been done and shared report to Emcure Team
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 30
Effort burnt till date : 156
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings
Meetings get postponed due to unavailability of Emcure stack holders