## Slide 1
Completed the following
  Integrated requirement for finance and other users related to PIDF
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Get the detail over SSO, as per Emcure team it supposed to be finalized by june 1st week.
Accomplishment for the week
Status update for the week 30th May 2022 to 3rd June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Updating wireframes for finance and commercial user
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 21
Effort burnt till date : 425
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 2
Completed the following
  Integrated requirement for finance and other users related to PIDF
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Update the wireframe / SRS with latest changes
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Get the detail over SSO, as per Emcure team next revision will be on 17th June
Accomplishment for the week
Status update for the week 6th June 2022 to 10th June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure stakeholders for requirement gathering
Updating wireframes for finance and commercial user
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 28
Effort burnt till date : 453
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 3
Completed the following
  Integrated requirement for finance and other users related to PIDF
  Prepare SRS with updated modules
  Prepare document with % of work gathered & signoff
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Get the detail over SSO
Accomplishment for the week
Status update for the week 13th June 2022 to 17th June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure stakeholders for requirement gathering
Shared updated version of wireframe & SRS document
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 8
Effort burnt till date : 461
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 4
Completed the following
  Integrated requirement for finance and other users related to PIDF
  Prepare SRS with updated modules
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 20th June 2022 to 24th June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure teamfor requirement gathering over finance & commercial module
Integrated changes in work flow diagram
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 9
Effort burnt till date : 470
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 5
Completed the following
  Integrated requirement for finance and other users related to PIDF
  Prepare SRS with updated modules
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 27th June 2022 to 1st July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure teamfor requirement gathering & Shared updated version of SRS document
Mr Gautam said sign-off over PDF will take 1-2 more weeks. Its expected to be done by 15th July.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 2.5
Effort burnt till date : 472.5
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase