## Slide 1
Completed the following
  Completed the PIDF minor changes, as discussed with Rahul
  Flow changes in NPD Workflow diagram completed.
  As per the discussion with the Emcure team on 29th April 2022, planning to go with the service - oriented architecture (SOA) for NPD application. The application will be hosted over on-Premise IIS server.
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Requirement Gathering for Dossier, Project
& Artwork module
Submission of the architecture diagram.
Based on SRS / wireframes sign-off, need to plan for the development phase
Accomplishment for the week
Status update for the week 2nd May 2022 to 6th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Confirmed architecture / pattern for application
Confirmed infrastructure for NPD application
Completed minor changes over PIDF
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 11
Effort burnt till date : 321
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Unavailability of relevant stakeholders to complete the req gathering process
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 2
Completed the following
  Shared all the important documents of project with Gautam
  Prepared the new architecture diagram and shared with Emcure team for approval.
  Received sign-off from few stakeholder
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Approval over the architecture diagram
Once we have sign-off begin with solution architect phase
Base line the pending modules requirment
Finalize the requirement traceability matrix & share with Emcure team
Accomplishment for the week
Status update for the week 9th May 2022 to 13th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Shared all the important documents with Mr. Gautam Kantak
Prepared architecture diargam and shared for approval
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 24
Effort burnt till date : 345
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 3
Completed the following
  Understand the Finance & Commercial details
  Prepared raw wireframe in excel for the finance & commercial module
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Base line the pending modules requirment
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 16th May 2022 to 20th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Started adopting pending module into wireframe using existing application & proposal
Begin with finance & commercial user module
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 40
Effort burnt till date : 385
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase
Meetings with BA for finance module has rescheduled

## Slide 4
Completed the following
  Set up steering committee meeting and took decision about development phase
  Integrated requirement for finance and other users related to PIDF
Effort Summary
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Base line the pending modules requirment (Artwork, Dossier, Project)
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 23th May 2022 to 27th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Started adopting pending module into wireframe using existing application & proposal
Integrated all the relevant changes for finance and commercial module
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Total Effort : 3510
Effort burnt this week : 19
Effort burnt till date : 404
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase