## Slide 1
Rachit Goyal identified as secondary business analyst
Completed the following
  Kick-off presentation
  Requirements gathering plan
  High level understanding about the application
  Identification of system masters
  Flow diagram
  Department wise form input mapping
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the source code & database for utilize in new application
Identify modules to be utilize from the existing application
Requirement Gathering for modules
Accomplishment for the week
Status update for the week 7th Mar 2022 to 11th Mar 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Project kick-off happened on 7th March 2022
Begin with requirement gathering phase
Received existing application source code & database for analysis
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the VPN & Tillomed system credential
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings

## Slide 2
Completed the following
  Set up existing application in NeoSOFT environment
  Created communication & code analysis plan
  Flow diagram
  Department wise form input mapping
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the source code & database
Identify modules to be utilize from the existing application
Requirement Gathering for modules
Creating wireframes
Prepare code analysis report
Accomplishment for the week
Status update for the week 14th Mar 2022 to 18th Mar 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 
Created work flow, data transmission between department
Begin with creating wireframe of modules
Begin with code analysis for utilize into new app
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Steering meeting to be setup for communication plan
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings

## Slide 3
Completed the following
  Flow diagram finalization
  Created wireframe for PIDF & PBF
  Created wireframe for masters
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the complete source code & database
Prepare report of code analysis & reutilization
Requirement Gathering for modules
Creating wireframes
Begin with writing SRS document
Accomplishment for the week
Status update for the week 21st Mar 2022 to 25th Mar 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 
Created wireframe for masters & PIDF form
Gone through with every screen, source code & database schemas
Understanding about mapping between PIDF & PBF
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Share the code analysis report at earliest
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings

## Slide 4
Completed the following
  Code analysis report
  PIDF & PBF flow
  Wireframe for 50-60% modules.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Requirement Gathering for Dossier, Project & Artwork module
Creating wireframes & SRS document
Base line all the requirement and prepare document for signoff
Accomplishment for the week
Status update for the week 28th Mar 2022 to 1st Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Baseline the requiredment for 50-60% modules
Code Analysis has been done and shared report to Emcure Team
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the required details from Emcure at earliest so pending modules can be analyzed in next week.
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in required details / schedule meetings
Meetings get postponed due to unavailability of Emcure stack holders

## Slide 5
Completed the following
  Prepared the wireframe for common, PIDF & PBF modules
  Prepared SRS document and shared with Emcure team to get signoff
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Analyze the baselline requirement with proposal to create CR report
Once we will receive signoff over shared SRS begin with development
Base line the pending modules requirmeent
Accomplishment for the week
Status update for the week 4th Apr 2022 to 8th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Baseline the requirment for common modules, PIDF & PBF.
SRS and Wireframe has been prepared and shared with Emcure team to get signoff
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the signoff on shared SRS from Emcure. Begin with pending baseline requirement so BA phase can finish as per planned
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
More changes are happening with wireframe / SRS & Delays in baseline requirement
Delays in getting signoff over SRS

## Slide 6
Completed the following
  Integrated CR for PIDF & PBF module.
  Updated SRS document and shared with Emcure team to get signoff
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Get sign-off on the SRS & Wireframe shared
Begin with development, once we will have base details.
Base line the pending modules requirmeent
Accomplishment for the week
Status update for the week 11th Apr 2022 to 15th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
SRS and Wireframe has been prepared and shared with Emcure team to get signoff
Share details required before begin with development phase.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the signoff on shared SRS from Emcure.
Get the base details to begin wit development
Begin with pending requirement
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
More changes are happening with wireframe / SRS & Delays in baseline requirement
Delays in getting signoff over SRS
Delays in complete the requirement gathering phase

## Slide 7
Completed the following
  Integrated CR for PIDF & PBF module.
  Updated SRS document and shared with Emcure team to get signoff
  Received Verbal sign off from the Emcure team (SID).
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Get clear sign-off email from Emcure team.
Begin with solution architect, once we will have base details.
Base line the pending modules requirment
Clear out all the technical details for this project.
Accomplishment for the week
Status update for the week 18th Apr 2022 to 22th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Updated SRS, Wireframe has been prepared, shared with Emcure team to get sign-off
Share details required before begin with development phase.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the clear signoff on shared SRS from Emcure.
Get the base details to begin wit development
Begin with pending requirement
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Technical details are not finalized, Delay while getting base details to begin with development
Delays in getting signoff over SRS
Delays in complete the requirement gathering phase

## Slide 8
Completed the following
  Different architecture option document
  Received sign-off from few stakeholder
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the technical approach
Begin with solution architect, once we will have base details.
Base line the pending modules requirment
Clear out all the technical details
Accomplishment for the week
Status update for the week 25th Apr 2022 to 29th Apr 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Prepare consolidated document with different approach to begin with development
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Get the base details to begin wit development
Begin with pending requirement
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Technical details are not finalized
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 9
Completed the following
  Completed the PIDF minor changes, as discussed with Rahul
  Flow changes in NPD Workflow diagram completed.
  As per the discussion with the Emcure team on 29th April 2022, planning to go with the service - oriented architecture (SOA) for NPD application. The application will be hosted over on-Premise IIS server.
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Requirement Gathering for Dossier, Project
& Artwork module
Submission of the architecture diagram.
Based on SRS / wireframes sign-off, need to plan for the development phase
Accomplishment for the week
Status update for the week 2nd May 2022 to 6th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Confirmed architecture / pattern for application
Confirmed infrastructure for NPD application
Completed minor changes over PIDF
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Begin with pending requirement
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Unavailability of relevant stakeholders to complete the req gathering process
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 10
Completed the following
  Shared all the important documents of project with Gautam
  Prepared the new architecture diagram and shared with Emcure team for approval.
  Received sign-off from few stakeholder
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Approval over the architecture diagram
Once we have sign-off begin with solution architect phase
Base line the pending modules requirment
Finalize the requirement traceability matrix & share with Emcure team
Accomplishment for the week
Status update for the week 9th May 2022 to 13th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Shared all the important documents with Mr. Gautam Kantak
Prepared architecture diargam and shared for approval
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Begin with pending requirement
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 11
Completed the following
  Understand the Finance & Commercial details
  Prepared raw wireframe in excel for the finance & commercial module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Base line the pending modules requirment
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 16th May 2022 to 20th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Started adopting pending module into wireframe using existing application & proposal
Begin with finance & commercial user module
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Begin with pending module requirement phase
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase
Meetings with BA for finance module has rescheduled

## Slide 12
Completed the following
  Set up steering committee meeting and took decision about development phase
  Integrated requirement for finance and other users related to PIDF
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Base line the pending modules requirment (Artwork, Dossier, Project)
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 23th May 2022 to 27th May 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Started adopting pending module into wireframe using existing application & proposal
Integrated all the relevant changes for finance and commercial module
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Begin with pending module requirement phase (Artwork, Dossier, Project)
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 13
Completed the following
  Integrated requirement for finance and other users related to PIDF
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Get the detail over SSO, as per Emcure team it supposed to be finalized by june 1st week.
Accomplishment for the week
Status update for the week 30th May 2022 to 3rd June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Updating wireframes for finance and commercial user
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 2
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 14
Completed the following
  Integrated requirement for finance and other users related to PIDF
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Update the wireframe / SRS with latest changes
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Get the detail over SSO, as per Emcure team next revision will be on 17th June
Accomplishment for the week
Status update for the week 6th June 2022 to 10th June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure stakeholders for requirement gathering
Updating wireframes for finance and commercial user
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 15
Completed the following
  Integrated requirement for finance and other users related to PIDF
  Prepare SRS with updated modules
  Prepare document with % of work gathered & signoff
  Emcure team have identified SPOC person who will provide sign-off over PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Get the detail over SSO
Accomplishment for the week
Status update for the week 13th June 2022 to 17th June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure teamfor requirement gathering & Shared updated version of SRS document
Mr Gautam said sign-off over PDF will take 2 more weeks. Its expected to be done by 1st July.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 16
Completed the following
  Integrated requirement for finance and other users related to PIDF
  Prepare SRS with updated modules
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 20th June 2022 to 24th June 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure teamfor requirement gathering over finance & commercial module
Integrated changes in work flow diagram
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 17
Completed the following
  Integrated requirement for finance and other users related to PIDF
  Prepare SRS with updated modules
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 27th June 2022 to 1st July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Meeting with Emcure teamfor requirement gathering & Shared updated version of SRS document
Mr Gautam said sign-off over PDF will take 1-2 more weeks. Its expected to be done by 15th July.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 18
Completed the following
  Integrated changes in PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 4th July 2022 to 8th July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 19
Completed the following
  Integrated changes in PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 11th July 2022 to 15th July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 20
Completed the following
  Integrated changes in PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 18th July 2022 to 22nd July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 21
Completed the following
  Integrated changes in PIDF module
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Sign-off over the SRS & wireframe
Working on finance & commercial module wireframe
Accomplishment for the week
Status update for the week 25th July 2022 to 29th July 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Waiting for sign-off over wireframe & SRS
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Sign - off over the wireframe & SRS.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in getting signoff over SRS for all stakeholders
Delays in complete the requirement gathering phase

## Slide 22
Completed the following
  Integrated changes in PIDF module
  Sign-off over partial modules
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Discuss about modules which has been signed off with current scope
Accomplishment for the week
Status update for the week 1st August 2022 to 5th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Received high level sign-off from Emcure team on SRS & wireframe shared
Integrated minor changes in wireframe with screens and linking
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Discuss about the signed off modules and identify closed scope.
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Delays in complete the requirement gathering phase

## Slide 23
Completed the following
  CR Report
  Identify signed - off modules
  Scheduled meeting with Emcure stakeholder to discuss about key pointers before begin with development
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Discuss about key pointers before begin with development phase
Discuss about CR, Commercial & mile stone
Accomplishment for the week
Status update for the week 8th August 2022 to 12th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Identify all the modules which has been signed off
Prepare role metrix for PIDF module
Prepare CR report as per signed off scope
Discuss about development infra and commercial
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Share CR list with Emcure team and confirmation about development infra
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0

## Slide 24
Completed the following
  Integrate changes in dashboard module.
  Integrate minor changes into SRS & wireframe
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Finalize the project planning document
Confirmation over commercial milestone & development infrastructure
Accomplishment for the week
Status update for the week 15th August 2022 to 19th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Begin with preparing project planning for development phase
Commercial and mile stone.
Development Infrastructure
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
Project plan
Development Infra
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0
Commercial milestone
Development infrastructure

## Slide 25
Completed the following
  Project Planning document
  CR Report
Key Action Items
Planned Key Milestones
Milestone Legend
NPD Web Application
Close the pre development pointers
Accomplishment for the week
Status update for the week 22nd August 2022 to 26th August 2022
Phase | Plan Start date | Plan End date | Actual Start date | Actual End date
Kick-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 | 7-Mar-22
Req. gathering | 7-Mar-22 | 15-Apr-22 | 7-Mar-22 | 
Code Analysis | 9-Mar-22 | 25-Mar-22 | 11-Mar-22 | 29-Mar-22
Solution Architect | 18-Apr-22 | 13-May-22 |  | 
Database Design | 18-Apr-22 | 22-Apr-22 |  | 
Development | 25-Apr-22 | 15-Jul-22 |  | 
Updated project planning document and marked with V1.
Updated CR report with V4 version.
Finalized the Commercial and development milestone.
Key Risks
PM : Nilesh Jain
Project overall progress
Key activities for next week
Completed
On Track
At Risk
Delayed
Yet to start
Project current Status
important pointers to be closed before begin with development phase
Resources
PM : 1
BA : 1
Dev : 0
Arct : 0
Tester: 0