## Sheet1
Id | Task | Start Date | EndDate | Dependency
1 | Phase 2 Development |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0
3 | Select API suppliers
4 | Formulation Finalised | Formulation TDP(Final Formulation Approved) | R&D(Pivotal batches manufactured completed) | 0
5 | Manufacture Pivotal batches | R&D(Pivotal batches manufactured completed) | R&D (Day 0) | 4
6 | Test and Place on Stability | R&D (Day 0) |  | 5
7 | Country Forecasts
8 | Carry out Biostudy
9 | 3 month stability Report | R&D (3 months) | R&D (3 months) +30 Days | 0
10 | 6 month stability Report | R&D (6 months) | R&D (6 months) +30 Days | 0
11 | Give last data to RA | R&D(Last data to Regulatory) | R&D (Last data to Regulatorys) +30 Days | 0
12 | Phase 3 Regulatory
13 | Country Forecasts
14 | Dossier Ready Date | RA (Dossier Ready Date) | RA(File Quality Date (Green/Orange/Red))
15 | Submit DCP in interested EU countries
| Submit DCP1 into Germany | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days
| Submit DCP1 into France | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days
| Submit DCP1 into Italy | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days
| Submit DCP2 into Germany | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days
| Submit DCP2 into France | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days
| Submit DCP2 into Italy | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days
16 | Submit into Nationals
| Submit Nationals into UK | RA (Submission Date) | RA (Submission Date)+5 Days
| Submit Nationals into India | RA (Submission Date) | RA (Submission Date)+5 Days
17 | DCP Validation
| Validation DCP1 into Germany | RA(Validation Date) | RA(Validation Date)+14 Days
| Validation DCP1 into France | RA(Validation Date) | RA(Validation Date)+14 Days
| Validation DCP1 into Italy | RA(Validation Date) | RA(Validation Date)+14 Days
| Validation DCP2 into Germany | RA(Validation Date) | RA(Validation Date)+14 Days
| Validation DCP2 into France | RA(Validation Date) | RA(Validation Date)+14 Days
| Validation DCP2 into Italy | RA(Validation Date) | RA(Validation Date)+14 Days
18 | DCP Starts | RA(Day 0) | RA(Day 106)
19 | DCP Day 106 | RA(Day 106) | RA(Day 210)
20 | DCP End of Procedure (EOP) | RA(End of Proc) | RA(End of Proc) +1 Days
21 | UK Validation | RA(Validation Date) | RA(Validation Date)+14 Days
| India Validation | RA(Validation Date) | RA(Validation Date)+14 Days
22 | Submit Nationals in other interested countries
23 | Pharmacovigilance requirements
24 | DCP Approval in NL | RA (MA Approval) | RA (MA Approval)
25 | DCP Approval in LT + HR | RA (MA Approval) | RA (MA Approval)
26 | DCP Approval in IT | RA (MA Approval) | RA (MA Approval)
27 | Approval in rest DCP countries | RA (MA Approval) | RA (MA Approval)
28 | Approval in UK | RA (MA Approval) | RA (MA Approval)
29 | Approval in other nationals | RA (MA Approval) | RA (MA Approval)
30 | Phase 4 Pre Launch Preparation per country
31 | Purchase order raised
| Purchase order raised Germany | Country (Purchase Order for launch stock) | Country (Purchase Order for launch stock)
| Purchase order raised Italy | Country (Purchase Order for launch stock) | Country (Purchase Order for launch stock)
| Purchase order raised France | Country (Purchase Order for launch stock) | Country (Purchase Order for launch stock)
32 | API ordered
| API ordered Germany | Bus Dev (PO Raised) | Bus Dev (PO Raised)
| API ordered Italy | Bus Dev (PO Raised) | Bus Dev (PO Raised)
| API ordered France | Bus Dev (PO Raised) | Bus Dev (PO Raised)
33 | Cutter Guides sent to Artwork
34 | Draft Artworks completed | Artwork (Draft Completed) | Artwork (Draft Completed)
35 | Artworks submitted and approved | Country (Artwork Submitted to HA) | Country (Artwork Submitted to HA)
36 | Plan Batch manufacture
37 | Phase 5 Launch Activities per country
38 | Final Artworks sent to plant
39 | Packaging for launch stock ordered
40 | Manufacture Launch Bulk Stock
41 | Approve Bulk product
42 | Packaging for launch stock received
43 | Launch Bulk packed
44 | Approve Finished product
45 | Send product to Europe
46 | Release product in Europe
47 | Send product to Country
48 | Obtain Price in Country
49 | Launch in Country