## In house plan
Id | Task | Start Date | EndDate | Dependency | Tab that data comes from | Name of field(s)
1 | Development Phase |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0 | Formulation TDP | API ordered + API Received
3 | Select API suppliers | Formulation TDP(API Received)+3 MONTHS | Formulation TDP(API Received)+3 MONTHS +1 Day | 2 | Formulation TDP
4 | Formulation Finalised | D4 + 3months | C5 + 1 day | 3 | Formulation TDP | Final Formulation Approved
5 | Manufacture Pivotal batches | D5 + 1month | C6 + 7 days | 4 | R&D | Pivotal Batches Manufactured Completed
6 | Test and Place on Stability | D6 + 1 day | C7 + 1 month | 5 | R&D | D7 = Day 0
7 | Carry out Biostudy | D7 + 3 months | C8 + 2 months | 6 | Biostudy | D8 = Date Of Final Report
8 | 3 month stability Report | D7 + 4 months | C9 | 6 | R&D | D9 = 3 months
9 | 6 month stability Report | C9 + 3 months | C10 | 8 | R&D | D10 = 6 months
10 | Give last data to RA | the latest of D7 + D10 + 1 month | C11 | 7+9 | R&D | D11 = Last Data To Regulatory
11 | Regulatory Phase | D11 | D46 or D48 whichever is latest | 10
Receipt date from RnD
12 | Dossier Ready Date |  |  | 10 | RA | Country wise separate line item based on submission type
| Dossier submission date |  |  |  |  | Country wise separate line item based on submission type
34 | End of Procedure (EOP) date |  |  | 33 | RA | Country wise separate line item based on submission type
| Country approval Date |  |  |  |  | Country wise separate line item based on submission type
37 | Earliest Launch date |  |  | 12 | RA | Country wise separate line item based on submission type
Phase 4 Pre Launch Preparation per country
47 | Purchase order raised | 12 months before launch date |  | 74 | Country | Country wise separate line item based on submission type
51 | API ordered | D47 | C47 + 14 days | 50 | Operations | Country wise separate line item based on submission type
55 | Cutter Guides sent to Artwork | EOP date - 1 month | C22 | 34 | Operations | Cutter Guides sent to plant
56 | Draft Artworks completed | D22 + 25 days | C23 | 58 | Artwork | Artworks completed
57 | Artworks submitted and approved | D23+6 days | C24 | 59 | Artwork | Artworks submitted and approved
58 | Plan Batch manufacture | Country approval whichever date is earlier | C25+15 days | 39, 41, 43, 44, 45 |  | Batch manufacture
| Phase 5 Launch Activities per country |  |  |  |  | country Launch
60 | Final Artworks sent to plant |  |  |  | Artwork | Date sent to plant
61 | Packaging for launch stock ordered |  |  | 62 |  | Packaging for launch stock ordered
62 | Manufacture Launch Bulk Stock |  |  | 39, 41, 43, 44, 45 | Operations | Launch Bulk Stock Manufactured
63 | Approve Bulk product |  |  | 62 | Quality | Approve Bulk Product
64 | Packaging for launch stock received |  |  | 61 | Operations | Packaging for launch stock received
65 | Launch Bulk packed |  |  | 62, 64 | Operations | Launch Bulk packed
66 | Approve Finished product |  |  | 65 | Quality | Approve Finished product
67 | Send product to Europe |  |  | 66 | Logistics | "Plant dispatch date" to "Arrival Port in EU"
68 | Release product in Europe |  |  | 67 | Quality | Release Finished Product
69 | Send product to Country |  |  | 68 | Logistics | "Despatch Date in EU" to "Arrival in country"
70 | Obtain Price in Country |  |  | 41, 43 | Country Tabs | Country Price
71 | Launch in Country Germany | 4 months after approval |  | 39 | Germany Country | Launch date country wise separate line item

## Third Party Plan
Id | Task | Start Date | EndDate | Dependency | Tab data comes from
1 | Phase 2 Development |  |  | 0
2 | Purchase API | Formulation TDP(API ordered) | Formulation TDP(API Received) | 0
3 | Select API suppliers | Formulation TDP(API Received)+3 MONTHS | Formulation TDP(API Received)+3 MONTHS +1 Day | 2
4 | Formulation Finalised | D4 + 3months | C5 + 1 day | 3
5 | Manufacture Pivotal batches | D5 + 1month | C6 + 7 days | 4
6 | Test and Place on Stability | D6 + 1 day | C7 + 1 month | 5
7 | Carry out Biostudy | D7 + 3 months | C8 + 2 months | 6
8 | 3 month stability Report | D7 + 4 months | c9 | 6
9 | 6 month stability Report | C9 + 3 months | c10 | 8
10 | Give last data to RA | Date from 3rd party company | C11
11 | Phase 3 Regulatory
12 | Dossier Ready Date | D11 + 1month | C13 | 10
13 | Submit DCP in interested EU countries - DCP1 | d13 + 7 days | C14 | 12
14 | RA Submission Dues Paid into Germany | D14 | D14 + 1 days | 13
15 | RA Submission Dues Paid into France | D14 | D14 + 1 days | 13
16 | RA Submission Dues Paid into Italy | D14 | D14 + 1 days | 13
17 | Submit DCP in interested EU countries - DCP2 |  |  | 10
18 | Submit DCP2 into Germany | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13
19 | Submit DCP2 into France | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13
20 | Submit DCP2 into Italy | RA (Submission Dues Paid) | RA (Submission Dues Paid) +1 Days | 13
21 | Submit into Nationals
22 | Submit Nationals into UK | D13 + 28 days | C23 | 12
23 | Submit Nationals into Israel | D13 + 90 days | C24 | 12
24 | DCP Validation
25 | Validation DCP1 into Germany | D15 | C26+14 Days | 14
26 | Validation DCP1 into France | D15 | C27+14 Days | 15
27 | Validation DCP1 into Italy | D15 | C28+14 Days | 16
28 | Validation DCP2 into Germany | RA(Validation Date) | RA(Validation Date)+14 Days | 18
29 | Validation DCP2 into France | RA(Validation Date) | RA(Validation Date)+14 Days | 19
30 | Validation DCP2 into Italy | RA(Validation Date) | RA(Validation Date)+14 Days | 20
| DCP Procedure | C33 | D35
31 | DCP Starts | the latest of D29, D30, D31 + 1 day | C33 | 25, 26, 27
32 | DCP Day 105 | D33 + 105 Days | C34 | 31
33 | DCP Day 106 | D34 + file coefficient (Red, Orange, Green) | C35 | 32
34 | DCP End of Procedure (EOP) | D35 + 104 days | C36 | 33
35 | UK Validation | D23 | C37+14 Days | 22
36 | Israel Validation | D24 | C38+14 Days | 23
37 | Submit Nationals in other interested countries | D13 + |  | 12
| Pharmacovigilance requirements | D13 + 90 Days | C36 - 1 month | 12
38 | National Phase in Germany | D36 | C41 + German Coefficient | 34
39 | DCP Approval in Germany | D41 | C42 | 38
40 | National Phase in France | D36 | C43 + France Coefficient | 34
41 | DCP Approval in France | D43 | C44 | 40
42 | National Phase in Italy | D36 | C45 + Italy Coefficient | 34
43 | DCP Approval in IT | D42 | C46 | 40
44 | Approval in UK | D37 + country coefficient | C47 | 35
45 | Approval in Israel | D38 + country coefficient | C48 | 36
Phase 4 Pre Launch Preparation per country
47 | Purchase order raised UK | 12 months before D77 | C50 | 74
48 | Purchase order raised Germany | 12 months before D74 | C51 | 71
49 | Purchase order raised Italy | 12 months before D76 | C52 | 73
50 | Purchase order raised France | 12 months before D75 | C53 | 72
51 | API ordered UK | D50 + 14 days |  | 50
52 | API ordered Germany | D51 + 14 days |  | 51
53 | API ordered Italy | D52 + 14 days |  | 52
54 | API ordered France | D53 + 14 days |  | 53
55 | Cutter Guides sent to Artwork | D36 - 1 month | C58 | 34
56 | Draft Artworks completed | D58 + 25 Days | C59 | 58
57 | Artworks submitted and approved | D59 + 6 Days | C60 | 59
58 | Plan Batch manufacture | First Approval either D42, D44, D46, D47, D48 | C61 + 14 Days | 39, 41, 43, 44, 45
Phase 5 Launch Activities per country
60 | Final Artworks sent to plant | C64 - 1 month
61 | Packaging for launch stock ordered | C65 - 2 months | C64 | 62
62 | Manufacture Launch Bulk Stock | First Approval either D42, D44, D46, D47, D48 Depending on country | C61 + 14 Days | 39, 41, 43, 44, 45
63 | Approve Bulk product | C65 | D65 + 28 Days | 62
64 | Packaging for launch stock received | D64 + 60 Days |  | 61
65 | Launch Bulk packed | C65 | D65 + 21 Days | 62, 64
66 | Approve Finished product | D68 | D68 + 14 Days | 65
67 | Send product to Europe | D69 | C70 + 28 Days | 66
68 | Release product in Europe | D70 | C71 + 14 Days | 67
69 | Send product to Country | D71 | C72 + 3 Days | 68
70 | Obtain Price in Country | Approval in Country | Depends on country | 41, 43
71 | Launch in Country Germany | 4 months after approval - D42 | C74 | 39
72 | Launch in Country Italy | 4 months after approval - D44 | C75 | 41
73 | Launch in Country France | 4 months after approval - D46 | C76 | 43
74 | Launch in Country UK | 4 months after approval - D47 | C77 | 44
75 | Launch in Country Israel | 4 months after approval - D48 | C78 | 45

## IPD
IPD
Patent Strategy | Wait for expiry | Develop around | Limit SmPC / Carve out | Litigation | Negotiation | Dropdown
Patent Type
Basic Patent Expiry | Other Limiting Patent Date 1 | Other Limiting Patent Date 2 | Earliest Launch Date
Any patents to be filed |  |  | Yes/No
Earliest market entry |  | Date | Validation to be kept or not
Estimated Number of generics in the market |  | Count and Names | As and when data is available - optional
| Law firm being used |  | As and when data is available - optional

## Reports
Reports
Stage wise Approved projects
Launch Plan

## Country
Market | Retail / Hospital or both
Launch Year | From RA
Country/region wise summary
| India | USA | Canada | Emerging Market
| Molecule + Pharmaceutical form |  | Launch year |  |  | Launch year +1 |  |  | Launch year +2 |  | Launch Stock required | Target Cost of Goods | Actual Cost of Goods | MS1 | MS2 | MS3 | MS1% | MS2% | MS3% | GM1 | GM2 | GM3 | GM1% | GM2% | GM3%
|  | Selling price | Units | Value | Selling price | Units | Value | Selling price | Units | Value | 3, 6, 9 Months
| Strength 1 Pack size 1 |  |  | =C10xD10 |  |  | =F10xG10 |  |  | =I10xJ10 | =D10*M9/12 |  | From Finance
| Strength 1 Pack size 2 |  |  | =C11xD11 |  |  | =F11xG11 |  |  | =I11xJ11 | =D11*M9/12 |  | From Finance
| Strength 1 Pack size n |  |  | =C12xD12 |  |  | =F12xG12 |  |  | =I12xJ12 | =D12*M9/12 |  | From Finance
| Strength 2 Pack size 1 |  |  | =C13xD13 |  |  | =F13xG13 |  |  | =I13xJ13 | =D13*M9/12 |  | From Finance
| Strength 2 Pack size 2 |  |  | =C14xD14 |  |  | =F14xG14 |  |  | =I14xJ14 | =D14*M9/12 |  | From Finance
| Strength 2 Pack size n |  |  | =C15xD15 |  |  | =F15xG15 |  |  | =I15xJ15 | =D15*M9/12 |  | From Finance
| Strength n Pack size 1 |  |  | =C16xD16 |  |  | =F16xG16 |  |  | =I16xJ16 | =D16*M9/12 |  | From Finance
| Strength n Pack size 2 |  |  | =C17xD17 |  |  | =F17xG17 |  |  | =I17xJ17 | =D17*M9/12 |  | From Finance
| Strength n Pack size n |  |  | =C18xD18 |  |  | =F18xG18 |  |  | =I18xJ18 | =D18*M9/12 |  | From Finance
| Tradename required | Yes / No | If yes | Tradename | date registered | Add in commercial form
| Purchase Order for launch stock | Date | Number |  |  | Add in commercial form

## Sheet1
RND
RA | RA will fill the input
Commercial
Countrywise | Launch dates

## Bus Dev
Agreed minimum orders | Pack size 1 | Pack size 2 | Pack size 3 | Pack size n
Strength 1 | 0 | 0 | 0 | 0
Strength 2 | 0 | 0 | 0 | 0
Strength 3 | 0 | 0 | 0 | 0
Strength n | 0 | 0 | 0 | 0

## RnD
R&D Responsible person | name
Type of development | Date from IP Tab
[5 empty] | API suppliers | Primary | Potential Alt. 1 | Potential Alt. 2 | API if In-house
API Supplier | =J3 | =J4 | =J5 |  | Supplier |  |  |  | Root of Synthesis
[5 empty] | Polymorph |  |  |  | Polymorph
Pivotal batches manufactured completed | Date | Cost ($) |  |  | Process (early c) |  |  |  | Process (early c)
Stability Results |  |  |  |  | Process (late c) |  |  |  | Process (late c)
Day 0 | Date | Estimate 1st date to be 1 month after C5 |  |  | Manufacturing site |  |  |  | Manufacturing site
3 months | Date | Estimate 1st date to be 3 months after C6 |  |  | Date of Site EU authority inspection | From Quality | From Quality | From Quality | Scheduled
6 months | Date | Estimate 1st date to be 3 months after C7 |  |  | Date of Site Tillomed inspection | From Quality | From Quality | From Quality | Filing time
[5 empty] | Lead time |  |  |  | Investments/Capex if Any
BE Study Results | Date from Bio Tab |  |  |  | DMF availability |  |  |  | Lead time
[5 empty] | Cost (R&D cost/KG) |  |  |  | Cost (R&D cost/KG)
Last date to Regulatory | Date | Estimate 1st date to be 1 month after C9 |  |  | Cost (commercial cost/KG) |  |  |  | Cost (commercial cost/KG)
Pack sizes on stability | Pack size 1 | Pack size 2 | Pack size 3 | Pack size n
Strength 1 | Types | Types | Types | Types
Strength 2 | Types | Types | Types | Types
Strength 3 | Types | Types | Types | Types
Strength n | Types | Types | Types | Types

## Formulation
Formulater Responsible person | name |  | Optional to decide with PM
Approach | QnQ formulation vs the innovator or are we changing the formulation/ Design around to avoid the patent | [7 empty] | From Patent TAB
TDP | Innovator |  |  | Emcure
Strength | x mg | y mg | z mg | x mg | y mg | z mg
Description:
Shape
Colour
Engraving
Packaging |  | PICTURE |  |  | PICTURE |  | Need to upload image
Primary
Secondary
Shelf-life
Storage / Handling
Estimated Annual Volume
Calculated from country tabs | Xmg | ymg | Zmg |  |  |  |  | pack size * Units * country = Tablets per year
Year 1
Year 2
Year 3
Non-standard product | Yes / No
Pivotals
Batch size
No. Batches per strength
Site transfer (if yes, when) | Date
API ordered | Date
API Received | Date
Formulation team could have extra milestones here if required
Final Formulation Approved | Date

## Post Development - Bio Strategy
Bio Responsible person | name | To decide with Mahesh Lolage
Is Bio Required?
RLD (MA number and country of origin) to be used for BE or for Dev
BE strength
Bio Requirements
Pilot and Pivotal Requirements
Complexity of Bio (IR, ER, liposomal, suspension)
Number of subjects
Duration of study
Type of study – As recommended by guidelines.
Country in which BE would be done.
BE study investment
RLD quantity required – single units
RLD cost per unit.
Pivotal batch manufactured | Date from R&D Tab
Date study Starts | Date
Date Study Finishes | Date
Full Cost of Study(ies) | 1000
Date of final Report | Date
Final Report number

## RA
RA Responsible person | name
Depending on file quality
Regulatory |  |  |  |  | Filing Strategy and countries |  |  | Day 0 | Date | Estimate 1st date to be 1 month after C12 |  |  | After validation
| Pivotal batch manufactured | Date from R&D Tab |  |  | Countries |  |  | Day 70 | =J3+70
[5 empty] | Earliest Submission - D Excl | From patent tab | 2 months post dossier ready date | Day 105 | =J3+105
| Last data from R&D | Date from R&D Tab |  |  | Earliest Launch - D Excl | From patent tab |  | Day 106 | Date | Estimate 1st date to be 2 months after J5 |  |  | File quality determines the date
[5 empty] | Alternate Salts |  |  | Day 120 | =J6+14
| BE Final Report | Date from Bio Tab | Number from Bio Tab |  | Recommended Ref Product |  |  | Day 150 | =J6+44
| List of countries |  |  |  | Non–standard product |  |  | Day 180 | =J6+74 |  |  |  | Therapeutic indications:
Tillomed | Type of Submission | DCP, CP, RUP, National, MRP | radio with multi select |  | Full application opportunity |  |  | Day 210 | =J6+104
[5 empty] | Sites and Labs |  |  | End of Proc | Date
| Dossier Ready Date | Date | Estimate 1st date to be 1 month after C6 | [6 empty] | Coefficient table
cannot be before the date from patent c5
| File Quality | Green/Orange/Red
| Earliest Submission - D Excl | From patent tab
CMS(Concerned member states) | Earliest Launch - D Excl | From patent tab | Dropdown | Input
DCP 1 | Procedure Number | Country | Strengths Required | Cost ($) | Submission Dues Paid | Validation | MA Approval | Post approval variations | MA Transfer | Launch | RA Status |  | Included and excluded indications by country
RMS Country | MA Number | Populate from PIDF data | Choice from list |  | Date | Date | Estimate date to be the country coeffient after J11. | Yes / No | Yes / No | From country |  | Dossier
CMS | MA Number | Country 1 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 2 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 3 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 4 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 5 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 6 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 7 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 8 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 9 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country n | Choice from list |  | Date | Date |  |  |  | From country
DCP 2 | Procedure Number | Country | Strengths Required | Cost ($) | Submission Dues Paid | Validation | MA Approval | Post approval variations | MA Transfer | Launch | RA Status |  | Included and excluded indications by country
RMS Country | MA Number | Country | Choice from list |  | Date | Date | Estimate date to be the country coeffient after J11. | Yes / No | Yes / No | From country
CMS | MA Number | Country 1 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 2 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 3 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 4 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 5 | Choice from list |  | Date | Date |  |  |  | From country
CMS | MA Number | Country 6 | Choice from list |  | Date | Date |  |  |  | From country
Nationals |  | Country | Strengths Required | Cost ($) | Submission Date | Validation Date | MA Approval | Post approval variations | MA Transfer | Launch | RA Status |  | Included and excluded indications by country
| MA Number | United Kingdom | Choice from list |  | Date | Date | Estimate date to be the country coeffient after F | Yes / No | Yes / No | From country
| MA Number | Country 1 | Choice from list |  | Date | Date |  | Yes / No | Yes / No | From country
| MA Number | Country 2 | Choice from list |  | Date | Date |  | Yes / No | Yes / No | From country
| MA Number | Country 3 | Choice from list |  | Date | Date |  | Yes / No | Yes / No | From country
| MA Number | Country 4 | Choice from list |  | Date | Date |  | Yes / No | Yes / No | From country
| Earliest Launch - D Excl | From patent tab
|  | strength 1 | strength 2 | strength 3 | strength 4
Shelf Life at submission
Batch Size Registered
Shelf Life Registered